## Test Case Template Example
| Project Name: | connect us | Test Designed by: | Monika Kolpe
| Module Name: | Ticketing System | Test Designed date: | 2021-12-07
| Release Version: |  | Test Executed by:
| Ticket: | T159778 | Test Execution date:
Pre-condition | Application related services must be active
Dependencies:
Test Priority | Medium
Description | Ticketing System
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Actual Result | Status | Tester date | developer | developer date
TC_1 | Department Master | To check department management is present in masters or not. | 1.click on masters. |  | After clicking on masters Department management option should be display. | As Expected | Pass | 2021-12-06
TC_2 |  | To check if click on department management it redirects or not. | 1.click on masters. |  | It should redirects to department master page. | As Expected | Pass
2.click on department management
TC_3 |  | To check whether we add data on clicking on add button | 1.click on masters. |  | Department should be added | As Expected | Pass
2.click on department management.
3.enter value in the department name field
4.click on add button
TC_4 |  | To check edit button is working or not. | 1.click on edit button. |  | It should be display edit department | As Expected | Pass
TC_5 |  | To check all fields are present or not. | 1.click on masters. |  | It should display department name, remark, is active fields. | it display only department name. | Fail |  |  | Solved
2.click on department management
TC_6 |  | To check view is available or not. |  |  | It should display data of particular department. | As Expected | Pass
TC_7 |  | To check the fields in view option |  |  | It should display department name, remark, is active, updated by and updated at fields. | display only sr no., department name and actions option. | Fail |  |  | Solved
TC_8 |  | To check the fields in edit option |  |  | Edit contains department name and remark and is active fields. | display only department name. | Fail |  |  | Solved
TC_9 |  | To check history option is present or not. |  |  | History master is used to view the changes in the particular department | history option is not present. | Fail |  |  | Not added in this scope
TC_10 |  | To check delete button is working or not. |  |  | Delete button deletes the particular department | delete button not working | Fail |  |  | Solved
TC_11 |  | To check department name accepts blank value | 1.click on masters. |  | Blank department name should not accepts. | It accepts blank department name | Fail |  |  | Solved
2.click on department management.
3.click on departnament name.
4.enter department name.
5.click on add button.
TC_12 |  | To check newly added department | 1.click on masters. |  | Newly added department should display first | newly added department add in the last | Fail |  |  | Solved
2.click on department management.
3.add new department.
TC_13 | Status Master | To check status management is present in masters or not. | 1.click on masters. |  | It should display status management option after clicking on masters. | As Expected | pass
2.click on status management.
TC_14 |  | To check if click on status management it redirects or not. |  |  | It should redirects to status master page. | As Expected | pass
TC_15 |  | To check view is available or not. |  |  | It should display data to the related ticket. | As Expected | Pass
TC_16 |  | To check the fields in view option |  |  | It should display status, remark, is active, updated by and updated at fields. | display only sr no., status and actions option. | Fail |  |  | Solved
TC_17 |  | To check if we click on add data data is added or not | 1.click on masters. |  | Data should be added in the status master. | Data not added. | Fail |  |  | Solved
2.click on status management.
3.enter value in the status field.
4.click on add button.
TC_18 |  | To check edit button is working or not. | 1.click on edit button. |  | It should be display edit department | edit is working | Pass
TC_19 |  | To check all fields in edit are present or not. | 1.click on masters. |  | It should display status, remark, is active fields. | it display only status. | Fail |  |  | Solved
2.click on status master.
TC_20 |  | To check history option is present or not. |  |  | History master is used to view the changes in the status of the ticket. | history option is not present. | Fail |  |  | Not added in this scope
TC_21 |  | To check delete button is working or not. |  |  | Delete button deletes the particular department | delete button not working | Fail |  |  | Solved
TC_22 |  | To check fields in the add option are mandatory or not | 1.click on masters. |  | The fields in the add button should mandatory | the fields are not mandatory | Fail |  |  | Solved
2.click on department management
3.click on add button.
TC_23 |  | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_24 |  | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_25 | Employee Master | To check employee management is present or not. | 1.click on masters. |  | It should display employee management option after clicking on masters. | As Expected | pass
2.click on employee management
TC_26 |  | To check if click on employee management it redirects or not. |  |  | It should redirects to employee master page. | As Expected | pass
TC_27 |  | To check add employee is working or not. | 1.click on masters. |  | After clicking on add employee it displays employee details | Add Employee is not working | Fail |  |  | pass
2.click on employee management.
TC_28 |  | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_29 |  | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_30 |  | To check click on employee management employee data is display or not | 1.click on masters. |  | It should be display employee master page with employee data. | Employee data not display. | fail |  |  | pass
2.click on employee management.
TC_31 | Role master | To check role management is present or not. | 1.click on masters. |  | It should be display role master. | As Expected | pass
2.click on role management.
TC_32 |  | To check if click on role management it redirects or not. | 1.click on masters. |  | After clicking on role management it redirects to role master page. | As Expected | pass
2.click on role management.
TC_33 |  | To check add data is working or not. | 1.click on masters. |  | It should display field details which we have add | add button not working | Fail |  |  | Solved
2.click on role management.
3.click on add button.
TC_34 |  | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_35 |  | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_36 |  | To check edit button is working or not. | 1.click on masters. |  | It should display edit page | edit button is not working. | Fail |  |  | Pass
2.click on role management.
3.click on edit button.
TC_37 |  | To check delete button is working or not. |  |  | It deletes the particular role. | delete button not working | Fail |  |  | Solved
TC_38 |  | To check view in the role master page. |  |  | It should display role master data of all roles. | displays role master data. | Pass
TC_39 | Navigation drawer | To check logo is present or not. |  |  | It should display logo of techneai and the word techneai | another logo is present | Fail | 2021-12-07 |  | Attachment and Images are not added in this scope
TC_40 |  | To check pages are present or not. |  |  | It should display pages | As Expected | pass
TC_41 |  | To check if click on any page it navigate to particular page or not. |  |  | It should navigate to particular page. | As Expected | pass
TC_42 |  | To check whether toggle is present or not. |  |  | It should display toggle. | As Expected | pass
TC_43 |  | To check if click on toggle then it hides navigation drawer or not |  |  | After click on toggle it hides navigation drawer. | Toggle button is not clickable. | Fail |  |  | Solved
TC_44 | Search Bar | To check whether seaarch bar is present or not |  |  | Search bar should be display. | As Expected | Pass
TC_45 |  | To check search bar is working or not |  |  | It used to search tickets, projects and worklists. | Search bar is not working. | Fail |  |  | Solved
TC_46 | Profile Content | To check profile content is present or not |  |  | It shows profile content | As Expected | Pass
TC_47 |  | To check profile content consists of profile picture, name and designation |  |  | It should displays profile picture of user, name and designation. | It displays profile picture, name. It does not show designation. | Fail |  |  | We have added nothing about profile in this scope
TC_48 |  | To check log out option is available or not after clicking on profile |  |  | After clicking on profile it should display the log out option | As Expected | Pass
TC_49 | Notification bell | To check notification bell is present or not |  |  | Notification bell will be there | As Expected | Pass
TC_50 |  | To check if click on notification bell it navigates to notification page or not. |  |  | After clicking on notification bell it notification page should open | As Expected | Pass
TC_51 |  | To check notification bell shows no of notifications or not. |  |  | It should display no of notifications | It shows only notification bell | Fail |  | Solved
TC_52 | User Master | To check user management option is available or not. | 1.click on masters. |  | It should display user management option. | As Expected | Pass
2.click on user management.
TC_53 |  | To check if click on user management it redirects or not. | 1.click on masters. |  | After clicking on masters user master option should be display. | As Expected | Pass
2.click on user management.
TC_54 |  | To check whether we add data on clicking add button | 1.click on masters. |  | It should redirects to user master page for creating new user | As Expected | Pass
2.click on user management.
3.enter value
4.click on add user button
TC_55 |  | To check edit button is working or not. | 1.click on masters. |  | It should display edit user details | It displays profile details | Fail |  | Solved
2.click on user master
3.click on edit button.
TC_56 |  | To check all fields in edit are present or not. | 1.click on masters. |  | It should display edit user details page with all the fields. | It displays profile details | Fail |  | Solved
2.click on user management.
3.click on edit button.
TC_57 |  | To check mandatory fields are showing or not. |  |  | It should display mandatory fields (asterisk symbol) | Mandatory fields are not present. | Fail |  | Solved
TC_58 |  | To check view is available or not. |  |  | It should display data of particular user. | It displays data of user but some fields are remaining. | Fail |  | Solved
TC_59 |  | To check the fields in edit option |  |  | It should display edit user page. | It displays user profile details. | Fail |  | Solved
TC_60 |  | To check history option is present or not. |  |  | History master is used to view the changes in the particular user | history option is not present. | Fail |  | History is not added
TC_61 |  | To check delete button is working or not. |  |  | Delete button deletes the particular user | delete button not working | Fail |  | Solved
TC_62 |  | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_63 |  | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_64 |  | To check fields in the create user page after clicking on add user. | 1.click on masters. |  | It displays full name, user name, email id, contact no, department, gender, address, city like fields. | All fields are not there. | Fail |  | Solved
2.click on user management.
3.click on add user.
TC_65 |  | To check fields are mandatory or not in create user page. | 1.click on masters. |  | mandatory fields should be shown using asterisk symbol. | Mandatory fields are not present. | Fail |  | Solved
2.click on user management.
3.click on add user.
TC_66 |  | To check user is created or not. |  |  | User should be added in the user master page. | User not added | Fail |  | Solved
TC_67 |  | To check create button is working or not. |  |  | After clicking on create button user should be added | create button not working | Fail |  | Solved
TC_68 |  | To check cancel button is working or not. |  |  | After clicking on cancel button back to the user master page. | cancel button not working | Fail |  | Solved
TC_69 |  | To check contact no field in the create user |  |  | Contact no should accepts the 10 digit number. | It accepts more than 10 digit number | Fail |  | Solved
TC_70 |  | To check fields in the view user master page are correct or not |  |  | It should display view of all users with full name, username, mailid, contact no, department, designation, gender, address, city, state, country, pincode, profile picture, password, remark, is active, updated by, updated at fields. | It displays only sr, name and actions. | Fail |  | Solved
TC_71 | Tickets | To check tickets tab is present or not |  |  | Tickets tab should display. | As Expected | pass
TC_72 |  | To check tickets tab contains the total, unsolved, progress and finished tickets or not. |  |  | It should contains total tickets, unsolved tickets, progress tickets and finished tickets. | Tickets tab contains ticket management and your tasks. | Fail |  | Initailly we have shown only user tickets
TC_73 |  | To check if click on tickets tab ticket management is present or not. |  |  | there should beoption of ticket management | As Expected | pass
TC_74 |  | To check after clicking on ticket management it redirects or not. | 1.click on masters. |  | It should display ticket master page | not redirects to ticket master page. | Fail |  | Solved
2.click on ticket management.
TC_75 |  | To check new ticket button is working or not | 1.click on masters. |  | It should displays create ticket page after clicking on new ticket button. | new ticket button is working | pass
2.click on ticket management.
3.click on new ticket.
TC_76 |  | To check tickets page |  |  | It should display tickets page which contains naviagtion drawer, search bar, home button, notification bell, profile content. | all fields are present but home button are not there | Fail |  | Solved
TC_77 |  | To check if click on new ticket then create page consists of fields to adding new ticket. |  |  | It should display all fields contains ticket id, type of issue, actual user, actual date, department, expected date, file upload, priority, description, submit, cancel. | It contains ticket id, type of issue, priority, description, tikcet date, department, user, submit and cancel. Actual user, actual date, expected date, file upload are missing. | Fail |  | File uploading is not there
TC_78 |  | To check ticket date accept correct date or not. |  |  | The date should be auto generated. | It accepts any date. | Fail |  | Solved
TC_79 |  | To check department in the create ticket page |  |  | Department contains the dropdown which consists of department names. | department names are not present. | Fail |  | Solved
TC_80 |  | To check priority field in the create ticket page |  |  | Priority should be display in radio buttons with priority values like high, medium, etc. | Priority contains dropdown | Fail |  | DropDown is easy for user as all option is in dropdown
TC_81 |  | To check mandatory fields are showing or not. |  |  | mandatory fields should be shown using asterisk symbol. | the fields are not mandatory | Fail |  | Solved
TC_82 |  | To check submit button is working or not. |  |  | After click on submit button ticket is added. | submit button not working | Fail |  | Solved
TC_83 |  | To check cancel button is working or not. |  |  | After clicking on cancel button it redirects to the ticket master page | cancel button is working | pass
TC_84 |  | To check home button is present or not in all managements page. |  |  | There is home button which is redirects to the hme page. | Home button is not present. | Fail |  | Solved
TC_85 | Dashboard | To check dashboard |  |  | It contains naviagtion drawer which contains logo, dashboard, projects like tabs | As Expected | pass
TC_86 |  | To check dashboard consists of tickets and worklists count. |  |  | It should display the count of tickets and worklists. | nothing shows on the dashboard. | Fail
TC_87 |  | To check if click on sign in button it redirects to the home page or not. |  |  | Home page should be open. | As Expected | pass
TC_88 | Your task | To check your tasks tab |  |  | After clicking on your task tab the tasks should be display | no data is present. | Fail |  | Solved
TC_89 | Communication Master | To check communication management is present in masters or not. | 1.click on masters and observe. |  | After clicking on masters Department management option should be display. | As Expected | Pass | 2021-12-18
TC_90 | Communication Master | To check if click on communication management it redirects or not. | 1.click on masters. |  | It should redirects to communication master page. | As Expected | Pass
2.click on communication management
TC_91 | Communication Master | To check whether add user button is working or not. | 1.click on masters. |  | Add user button should work properly | As Expected | Pass
2.click on communication management.
TC_92 | Communication Master | To check if click on add user button it redirects or not |  |  | After clicking on add user button it redirects to communication details page | As Expected | Pass
TC_93 | Communication Master | To check fields in the communication details page |  |  | communication type, subject and body this fields should be available to add new user | As Expected | Pass
TC_94 | Communication Master | To check data is added or not. | 1. click on add user button. |  | new user should be created | As Expected | Pass
2.enter all fields.
3. click on create button
TC_95 | Communication Master | To check create button is working or not. |  |  | Create button should be work properly | As Expected | Pass
TC_96 | Communication Master | To check cancel button is working or not. |  |  | After clicking on cancel button back to the communication master page. | As Expected | Pass
TC_97 | Communication Master | To check edit button is working or not. |  |  | After click on edit button it redirects to the edit page | It redirects user profile page | Fail
TC_98 | Communication Master | To check delete button is working or not. |  |  | After click on delete button the related data should be deleted. | delete button not working | Fail
TC_99 | Communication Master | To check communication type field accepts only characters |  |  | Communication type field accepts only characters | it accepts numeric values | Fail
TC_100 | Communication Master | To check subject field accepts only characters |  |  | Subject field accepts only characters | it accepts numeric values | Fail
TC_101 | Communication Master | To check body field accepts only characters |  |  | Body field accepts only characters | it accepts numeric values | Fail
TC_102 | Communication Master | To check newly created data present first or not |  |  | Newly added data should be present first | newly added data is at last | Fail
TC_103 | Communication Master | To check duplicate data is added or not |  |  | duplicate data should not added | duplicate data is added | Fail
TC_104 | Communication Master | To check mandatory fields are showing or not. |  |  | mandatory fields should be shown using asterisk symbol. | Mandatory fields are not present. | Fail
TC_105 | Country Management | To check country management option is available or not | 1.click on masters and observe. |  | Country management tab should be present in the masters | As Expected | Pass
TC_106 | Country Management | To check if click on country management it redirects or not | 1.click on masters |  | After click on country management it redirects to the country master page | As Expected | Pass
TC_107 | Country Management | To check country master page shows added data |  |  | Country master page should contains added data | nothing shows on the country master page | Fail
TC_108 | Country Management | To check country is added or not | 1.enter value in the country name field. |  | Country should be added | Country not added | Fail
2.click on add button
TC_109 | Customer Master | To check Customer management tab is present or not | 1.click on customer management |  | Customer Management option should be present | As Expected | Pass
TC_110 | Customer Master | To check when click on customer management it redirects or not | 1. click on customer management |  | After click on customer management it should redirects to the customer master page | As Expected | Pass
TC_111 | Customer Master | To check Add customer button is working or not | 1.click on customer management |  | After click on add customer button it redirects to the customer master create page | As Expected | Pass
2.click on add customer button
TC_112 | Customer Master | To check create button is working or not. |  |  | After click on create button data should be added | Data not added. | Fail |  |  | No Customer Module is there
TC_113 | Customer Master | To check all fields in the customer master page |  |  | Customer master page contains customer type, contact no, email id fields. | As Expected | Pass
TC_114 | Customer Master | To check cancel button is working or not. |  |  | After click on cancel button it redirects to the customer page | As Expected | Pass
TC_115 | Customer Master | To check edit button is working or not. | 1.click on masters |  | After click on edit button it redirects to the edit page | edit button is not working. | Fail |  |  | No Customer Module is there
2.click on customer management
3.click on edit button.
TC_116 | Customer Master | To check delete button is working or not. | 1.click on masters |  | After click on delete button the related data should be deleted. | delete button not working | Fail |  |  | No Customer Module is there
2.click on customer management
3.click on delete button.
TC_117 | Customer Master | To check data is added or not. |  |  | data should be added | Data not added. | Fail |  |  | No Customer Module is there
TC_118 | Designation Master | To check designation management tab is present or not | 1.click on masters and observe. |  | Designation management option should be present in the masters tab | As Expected | Pass
TC_119 | Designation Master | To check if click on designation management it redirects or not | 1.click on designation management |  | After clicking on designation management tab it redirects to the designation page. | As Expected | Pass
2.observe
TC_120 | Designation Master | To check Add designation button is working or not | 1.click on designation management |  | Add designation button should work properly. | As Expected | Pass
2.click on add designation button
TC_121 | Designation Master | To check if click on add designation button it redirects or not | 1.click on designation management |  | After click on add designation button it redirects to the designation/create page | As Expected | Pass
2.click on add designation button
TC_122 | Designation Master | To check data is added or not. |  |  | Data shouldbe added | As Expected | Pass
TC_123 | Designation Master | To check fields in the designation/create page |  |  | All fields should be present | As Expected | Pass
TC_124 | Designation Master | To check create button is working or not. |  |  | After click on create button data should be added | Data not added. | Fail |  |  | No Customer Module is there
TC_125 | Designation Master | To check cancel button is working or not. |  |  | After click on cancel button it should redirects to the designation page | cancel button not working | Fail |  |  | No Customer Module is there
TC_126 | Designation Master | To check designation field accepts right value or not | 1.click on masters. |  | designation field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail |  |  | No Customer Module is there
2.click on designation management
3.click on add designation
TC_127 | Designation Master | To check remark field accepts right value or not | 1.click on masters. |  | remark field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail
2.click on designation management
3.click on add designation
TC_128 | Designation Master | To check designation field accepts blank value or not | 1.click on masters. |  | designation field accepts characters, numbers, special characters. | it accepts blank value | Fail
2.click on designation management
3.click on add designation
TC_129 | Designation Master | To check remark field accepts blank value or not | 1.click on masters. |  | remark field accepts characters, numbers, special characters. | it accepts blank value | Fail
2.click on designation management
3.click on add designation
TC_130 | Designation Master | To check fields are mandatory or not. | 1.click on masters. |  | Fields should be mandatory | Mandatory fields are not present. | Fail
2.click on designation management
3.click on add designation
TC_131 | Designation Master | To check newly added data | 1.click on masters. |  | Newly added data should be present first | newly added data is at last | Fail
2.click on designation management
3.click on add designation
TC_132 | Designation Master | To check duplicate data is added or not |  |  | duplicate data should not added | duplicate data is added | Fail
TC_133 | Menu master | To check menu management tab is present or not | 1.click on masters and observe. |  | Menu management option should be present in the masters tab | As Expected | Pass
TC_134 | Menu master | To check if click on menu management it redirects or not | 1.click on menu management |  | After clicking on menu management tab it redirects to the menu page. | As Expected | Pass
2.observe
TC_135 | Menu master | To check Add menu button is working or not | 1.click on menu management |  | Add menu button should work properly. | As Expected | Pass
2.click on add menu button
TC_136 | Menu master | To check if click on add menu button it redirects or not | 1.click on menu management |  | After click on add menu button it redirects to the menu/create page | As Expected | Pass
2.click on add menu button
TC_137 | Menu master | To check data is added or not. |  |  | Data should be added | As Expected | Pass
TC_138 | Menu master | To check fields in the menu/create page |  |  | All fields should be present | As Expected | Pass
TC_139 | Menu master | To check create button is working or not. |  |  | After click on create button data should be added | As Expected | Pass
TC_140 | Menu master | To check cancel button is working or not. |  |  | After click on cancel button it should redirects to the designation page | As Expected | Pass
TC_141 | Menu master | To check menu name field accepts right value or not | 1.click on masters. |  | menu field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail
2.click on menu management
3.click on add menu
TC_142 | Menu master | To check menu type field accepts right value or not | 1.click on masters. |  | menu type field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail
2.click on menu management
3.click on add menu
TC_143 | Menu master | To check menu name field accepts blank value or not | 1.click on masters. |  | menu type field accepts characters, numbers, special characters. | it accepts blank value | Fail
2.click on menu management
3.click on add menu
TC_144 | Menu master | To check menu type field accepts blank value or not | 1.click on masters. |  | menu type field accepts characters, numbers, special characters. | it accepts blank value | Fail
2.click on menu management
3.click on add menu
TC_145 | Menu master | To check fields are mandatory or not. | 1.click on masters. |  | Fields should be mandatory | Mandatory fields are not present. | Fail
2.click on menu management
3.click on add menu
TC_146 | Menu master | To check newly added data | 1.click on masters. |  | Newly added data should be present first | newly added data is at last | Fail
2.click on menu management
3.click on add menu
TC_147 | Menu master | To check duplicate data is added or not |  |  | duplicate data should not added | duplicate data is added | Fail
TC_148 | Tenant Master | To check Tenant management tab is present or not | 1.click on masters and observe. |  | Tenanat management option should be present in the masters tab | As Expected | Pass
TC_149 | Tenant Master | To check if click on Tenant management it redirects or not | 1.click on tenant management |  | After clicking on tenant management tab it redirects to the menu page. | As Expected | Pass
2.observe
TC_150 | Tenant Master | To check Add tenant button is working or not | 1.click on tenant management |  | Add tenant button should work properly. | As Expected | Pass
2.click on add tenant button
TC_151 | Tenant Master | To check if click on add tenant button it redirects or not | 1.click on tenant management |  | After click on add tenant button it redirects to the tenant/create page | As Expected | Pass
2.click on add tenant button
TC_152 | Tenant Master | To check data is added or not. |  |  | Data should be added | Data not added. | Fail
TC_153 | Tenant Master | To check fields in the tenant/create page |  |  | All fields should be present | As Expected | Pass
TC_154 | Tenant Master | To check create button is working or not. |  |  | After click on create button data should be added | create button not working | Fail
TC_155 | Tenant Master | To check cancel button is working or not. |  |  | After click on cancel button it should redirects to the tenant page | cancel button not working | Fail
TC_156 | Employee Master | To check mandatory fields are showing or not. | 1.click on masters |  | mandatory fields should be shown using asterisk symbol. | Mandatory fields are not present. | Fail
2.click on employee management
3.click on add employee button
TC_157 | User master->Add->All dropdown | To check all dropdown are properly working or not. |  |  | dropdown list should be display. | it takes time to display dropdown list(loading). | Fail |  | Solved
TC_158 | User master->Add->cancel | To check cancel button is visible or not. |  | click here | cancel button should be display properly. | due to chat notification cancel button is hide. | Fail |  | Solved
TC_159 | Status Master->Add | To check status master's spelling is correctly written or not. |  |  | Spelling should be written correctly. | status spelling is incorrect. | Fail |  | Solved
TC_160 | Status Master->Add | To check status is added or not. |  |  | status should be added. | As Expected | pass
TC_161 | Status Master->Edit | To check status is updated or not. |  | click here | status should be updated. | As Expected | pass
TC_162 | Status Master->Delete | To check whether status is deleted or not |  | click here | after click on delete status should be removed. | status is not removing. | Fail
Solved
TC_163 | Status Master->Add | To check status textfield accepts only characters or not. |  |  | textfield should be accept no of characters according to user requirement. | sometime status textfield accepts only 10 characters. | Fail
Solved
TC_164 | Status Master->Add | To check whether status textfield accepts space or not. |  |  | textfield should be accept space between words. | It doesnt accept space in between. | Fail
Solved
TC_165 | Status Master->Add | To check whether duplicate data accepts or not. |  | click here | Duplicate entry should not be allowed. | duplicate entries accepts. | Fail
Solved
TC_166 | Status Master->Add | To check edit and delete button properly displayed or not. |  |  | button size should be proper. | buttons not display properly. | Fail
Solved
TC_167 | Status Master | To check all buttons are availble or not. |  |  | view and history button should be added. | buttons are not added. | Fail
TC_168 | Role Master | To check role textfield accepts only characters or not. |  |  | textfield should be accept only characters. | As Expected | pass
TC_169 | Role Master->add | To check whether textfield accepts space or not. |  | click here | space should be accept. | textfield doesnt accept the space. | Fail
Solved
TC_170 | Role Master->add | to check whether it accepts dot or not. |  | click here | It should not accept special characters except dot. | textfield doesnt accept dot. | Fail
Solved
TC_171 | Role Master->add | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | buttons not display properly. | Fail
Solved
TC_172 | Role Master->add | To check all buttons are availble or not. |  |  | view and history button should be added. | buttons are not added. | Fail
TC_173 | Role Master->add | To check whether duplicate data accepts or not. |  |  | Duplicate entry should not be allowed. | As Expected | Pass
TC_174 | Role Master->add | To check role textfield accepts only characters or not. |  |  | textfield should be accept no of characters according to user requirement. | sometime role textfield accepts only 10 characters. | Fail
Solved
TC_175 | Role Master->add | To check add button is working properly or not. |  |  | user role should be added. | sometimes add button is not working. | Fail
Solved
TC_176 | Department master | To check if click on department master whether it redirects or not. |  |  | It should be redirects to 'department Master' page. | As Expected | Pass
TC_177 | Department master | To check all buttons are availble or not. |  |  | view and history button should be added. | buttons are not added. | Fail
TC_178 | Department master | To check whether duplicate data accepts or not. |  |  | Duplicate entry should not be allowed. | As Expected | Pass
TC_179 | Department master | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | buttons not display properly. | Fail
Solved
TC_180 | In All Masters | To check after adding data successful message is received or not. |  |  | Successful message should be received in green color. | Successful message is displayed in red color. | Fail
Solved
TC_181 | Department master | To check delete button is working or not. |  | click here | record should be removed on click of delete. | Delete button is not working properly. | Fail
Solved
TC_182 | Department master->Add | To check whether added department is reflecting in user master or not. |  | click here | It should reflect in user master. | As Expected | pass
TC_183 | All masters->Add button | To check allignment of button is proper or not. |  |  | add button should be displayed in a center position. | not displaying in center. | Fail
Later
TC_184 | Designation Master | To check if click on Designation Master whether it redirects or not. |  |  | It should be redirects to 'designation Master' page. | As Expected | Pass
TC_185 | Designation Master | after adding duplicate data to check whether error message is displayed or not. |  |  | It should be display correct error message. | wrong error message is displaying. | Fail
Solved
TC_186 | Designation Master | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | buttons not display properly. | Fail
Solved
TC_187 | Designation Master | To check delete button is working or not. |  | click here | record should be removed on click of delete. | Delete button is not working properly. | Fail
Solved
TC_188 | Designation Master | To check all buttons are availble or not. |  |  | view and history button should be added. | buttons are not added. | Fail
TC_189 | Designation Master | To check whether textfield accepts space or not. |  |  | space should be accept. | textfield doesnt accept the space. | Fail
Solved
TC_190 | Designation Master | To check whether numbers accepts or not. |  | click here | numbers should not be accept. | it accepts numbers. | Fail
Solved
TC_191 | City Master | To check if click on City Master whether it redirects or not. |  | click here | It should be redirects to 'Add City' page. | As Expected | Pass
TC_192 | City Master | To check Add and cancel button is properly visible or not. |  | click here | add and cancel button should be display proper. | n letter is displayed between add cancel button. | Fail
Solved
TC_193 | City Master | To check the data is updated or not. |  |  | data should be update | updated changes is not reflecting. | Fail
Solved
TC_194 | City Master | To check while editing previous data is display or not. |  |  | previous entered data should be display while editing. | previous data is not displaying. | Fail
Solved
TC_195 | City Master | to check correct error message is displaying or not. |  | click here | correct error message should be display. | while updating city wrong error message is displayed. | Fail
Solved
TC_196 | City Master | To check delete button is working or not. |  | click here | record should be removed on click of delete. | Delete button is not working properly. | Fail
Solved
TC_197 | City Master | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | buttons not display properly. | Fail
Solved
TC_198 | City Master | To check all buttons are availble or not. |  |  | view and history button should be added. | buttons are not added. | Fail
Not required for now
TC_199 | State Master | To check if click on State Master whether it redirects or not. |  |  | It should be redirects to 'State Master' page. | As Expected | Pass
TC_200 | State Master->Add | To check Add button is working or not. |  |  | It should be redirects to 'Add State' page. | As Expected | Pass
TC_201 | State Master->Add | To check back button is available or not. |  |  | back button should be added. | back button is not available. | Fail
Not required for now
TC_202 | State Master->Add | To check without selecting country data is inserted or not. |  |  | there should be display warning message. | warning message is not displaying. | Fail
Solved
TC_203 | State Master->Add | To check duplicate data is acceptig or not. |  |  | Duplicate entry should not be allowed. | As Expected | Pass
TC_204 | State Master->Add | to check data is properly added or not. |  |  | data should be added. | As Expected | Pass
TC_205 | State Master->Add | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | buttons not display properly. | Fail
Solved
TC_206 | State Master->Add->state | To check textfield should accept only characters or not. |  | click here | textfield should accept characters only. | As Expected | Pass
TC_207 | State Master | To check edit and delete button properly working or not. or not. |  |  | record should be removed on click of delete. and record should be update on click of edit | edit and delete button is not working properly. | Fail
Solved
TC_208 | Country Master | To check if click on State Master whether it redirects or not. |  | click here | It should be redirects to 'Country Master' page. | As Expected | Pass
TC_209 | Country Master | To check Add and cancel button is properly visible or not. |  |  | space is needed berween the buttons | buttons are not proprly visible. | Fail
Solved
TC_210 | Country Master | To check while adding country space is accepted or not. |  |  | space should be accept. | space not accepts. | Fail
Solved
TC_211 | Country Master->Add | To check add bustton is working or not. |  | click here | country should be added. | As Expected | Pass
TC_212 | Country Master->Add | To check duplicate data is accepted or not. |  | click here | Duplicate entry should not be allowed. | duplicate entries accepts. | Fail
Solved
TC_213 | Country Master->Add | To check delete button is working or not. |  | click here | data should be removed on click of delete.delete successful message should be display. | message is not displaying after deleted specific record. | Fail
Solved
TC_214 | Country Master | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | buttons not display properly. | Fail
Solved
TC_215 | In all masters->Search bar | To check searchbar is working or not. |  |  | searched record should be display. | searchbar is not working. | Fail
TC_216 | User master | To check if click on User Master whether it redirects or not. |  |  | It should be redirects to 'User Master' page. | As Expected | Pass
TC_217 | User master | To check searchbar is working or not. |  |  | searched record should be display. | searchbar is not working. | Fail
TC_218 | User master->Add User | To check user details is added correct or not. |  | click here | user details should be added correctly. | wrong user details added multiple times. | Fail
Solved
TC_219 | User master->Add User->edit | While editing previous user details should be display. |  | click here | user details should be display. | previous user details is not showing | Fail
Solved
TC_220 | User master->Add User->edit | To check update functionality is working or not. |  | click here | updated data should be display correctly. | As Expected | pass
TC_221 | User master->Add User->edit | To check all buttons are availble or not. |  | click here | view and history button should be added. | buttons are not added. | Fail
TC_222 | User master | To check edit and delete button properly displayed or not. |  |  | button size should be proper. | buttons not display properly. | Fail
Solved
TC_223 | User master->Add User->Name textfield | To check nametextfield should accept only alphabet values. |  |  | nametextfield should be accept only alphabet values. | As Expected | pass
TC_224 | User master->Add User- | To check fields are mondatory or not. |  |  | mandatory fields should not be empty. | Select role,select designation, select department,and address validation field need validation. | Fail
Solved
TC_225 | User master->Add User- | To check Add and cancel button is properly visible or not. |  |  | space is needed berween the buttons | buttons are not proprly visible. | Fail
Solved
TC_226 | User master->Add User->Email textfield | To check email textfield have proper validation or not. |  |  | without .and @ textfield should not accept the data. | textfield accepts the data without .and @. | Fail
Solved
TC_227 | User master->Add User->Edit | To check While editing mandatory fields are displayed or not. |  |  | mandatory fields should be display while editing. | mandatory fields are not display while editing. | Fail
Solved
TC_228 | User master->Add User->Delete | to check delete button is working or not. |  |  | record should be removed. | Delete button is not working properly. | Fail
Solved
TC_229 | User master->Add User | To check back button is available or not. |  |  | back button should be added. | back button is not available. | Fail
Not Required for now
TC_230 | Masters | To check masters tab expand or not. |  |  | on click of masters tab it should be expand. | masters tab is not expands. | Fail
TC_231 | User master->Add User->Username | To check username is accepts number or not. |  |  | username field should be accepts number. | username field doesnt accept number. | Fail
Not required
TC_233 | Dynamic Form | To check dynamic form tab is present or not. |  |  | Dynamic for tab should be present. | As Expected | Pass
TC_234 | Dynamic Form | To check if click on dynamic form tab it redirects or not. |  |  | Click on dynamic form tab it should redirects to the dynamic form page. | As Expected | Pass
TC_235 | Dynamic Form | To check width of the text field is present or not. |  |  | Width of the text field should be present. | As Expected | Pass
TC_236 | Dynamic Form | To check type of the field is present or not. |  |  | Type of field should be present. | As Expected | Pass
TC_237 | Dynamic Form | To check name of the field is present or not. |  |  | Name of the text field should be present. | As Expected | Pass
TC_238 | Dynamic Form | To check label of the text field is present or not. |  |  | Label of the text field should be present. | As Expected | Pass
TC_239 | Dynamic Form | To check all fields display properly or not. |  |  | All fields should be display properly. | As Expected | Pass
TC_240 | Dynamic Form | To check remove button is working or not. |  |  | Click on remove button particular record should be deleted. | Remove button not working. | Fail
TC_241 | Dynamic Form -> Add Row | To check if click on add row new row added or not. |  |  | Click on add row new row should be added. | As Expected | Pass
TC_242 | Dynamic Form -> View Form | To check if click on view form form is displayed or not. |  |  | Click on view form form should be displayed. | As Expected | Pass
TC_243 | Dynamic Form -> Hide Form | To check if click on hide form form is hide or not. |  |  | Click on hide form form should be hidden. | As Expected | Pass
TC_244 | Dynamic Form -> Name Field | To check name field is required or not. |  |  | Name field should be required. When submit data it should display message like name field should be required. | Message not display. | Fail | Solved
TC_248 | Dynamic Form | To check all fields having validation or not. |  |  | All fields should have validation. | Message not display when submit data. | Fail
TC_249 | Dynamic Form | To check when we add fields then for submitting data submit/save button is present or not. |  |  | For adding data submit/save button should be present. | Buttons not present | Fail | Button is already there
TC_250 | Dynamic Form | if we add two small labels to check whether it is added in same line or not. |  |  | two small lables should be added in single line. | two small lines not added in single line. | Fail | ?
TC_251 | Dynamic Form | if we select text type to check whether textfield accepts only text or not. |  |  | label should be accept only text. | label accepts numbers also. | Fail
TC_252 | Dynamic Form->Template Name | To check added template name is displayed or not. |  |  | template name should be display. | template name doesnt display. | Fail | Solved
TC_253 | Dynamic Form | To check after adding fields successful message is received or not. |  |  | successful message should be recevied. | successful message should be received. | Fail | Solved
TC_254 | Dynamic Form | all previous added dynamic form should be display. |  |  | added dynamic forms should be display. | added dynamic forms not displaying. | Fail | Form will display in ticket
TC_255 | Dynamic Form | if we select type radio to check whether it is displayed or not. |  | click here | radio button should be display. | radio button is not displaying. | Fail | It is now in R&D
TC_256 | Dynamic Form | To check edit is working or not. |  |  | on click of edit should redirect form page. | it is redirecting tickit page. | Fail | Solved
TC_257 | Dynamic Form | To check template name is displayed correct or not. |  |  | template name should be display correct. | same form name displayed. | Fail | Solved
TC_258 | Dynamic Form | To check edit and delete button properly displayed or not. |  | click here | button size should be proper. | delete button is not displaying proper. | Fail
TC_259 | Designation Master | To check spelling of designation master is correct or not. |  |  | Designation master spelling should be correct. | Designation master spelling is incorrect. | Fail
Solved