## Test Case Template Example
| Project Name: | connect us | Test Designed by: | Monika Kolpe
| Module Name: | Ticketing System | Test Designed date: | 2021-12-07
| Release Version: |  | Test Executed by:
| Ticket: | T159778 | Test Execution date:
Pre-condition | Application related services must be active
Dependencies:
Test Priority | Medium
Description | Ticketing System
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Actual Result | Status | Developer | Tester
TC_1 | Login | To check login is successfully done or not. |  |  | Login should be successfully done. | As Expected | Pass
TC_2 | Department Master | To check department management is present in masters or not. | 1.click on masters. |  | After clicking on masters Department management option should be display. | As Expected | Pass
TC_3 | Department Master | To check if click on department management it redirects or not. | 1.click on masters. |  | It should redirects to department master page. | As Expected | Pass
2.click on department management
TC_4 | Department Master | To check whether we add data on clicking on add button | 1.click on masters. |  | Department should be added | As Expected | Pass
2.click on department management.
3.enter value in the department name field
4.click on add button
TC_5 | Department Master | To check edit button is working or not. | 1.click on edit button. |  | It should be display edit department | As Expected | Pass
TC_6 | Department Master | To check all fields are present or not. | 1.click on masters. |  | It should display department name, remark, is active fields. | it display only department name. | Fail |  | Pass
2.click on department management
solved
TC_7 | Department Master | To check view is available or not. |  |  | It should display data of particular department. | As Expected | Pass
TC_8 | Department Master | To check the fields in view option |  |  | It should display department name, remark, is active, updated by and updated at fields. | display only sr no., department name and actions option. | Fail |  | Pass
solved
TC_9 | Department Master | To check the fields in edit option |  |  | Edit contains department name and remark and is active fields. | display only department name. | Fail |  | Pass
solved
TC_10 | Department Master | To check history option is present or not. |  |  | History master is used to view the changes in the particular department | history option is not present. | Fail | solved | Pass
TC_11 | Department Master | To check delete button is working or not. |  |  | Delete button deletes the particular department | delete button not working | Fail |  | Pass
solved
TC_12 | Department Master | To check department name accepts blank value | 1.click on masters. |  | Blank department name should not accepts. | It accepts blank department name | Fail |  | Pass
2.click on department management.
3.click on departnament name.
|  |  | 4.enter department name. |  |  |  |  | solved
5.click on add button.
TC_13 | Department Master | To check newly added department | 1.click on masters. |  | Newly added department should display first | newly added department add in the last | Fail |  | Pass
2.click on department management.
3.add new department.
solved
TC_14 | Status Master | To check status management is present in masters or not. | 1.click on masters. |  | It should display status management option after clicking on masters. | As Expected | pass
2.click on status management.
TC_15 | Status Master | To check if click on status management it redirects or not. |  |  | It should redirects to status master page. | As Expected | pass
TC_16 | Status Master | To check view is available or not. |  |  | It should display data to the related ticket. | As Expected | Pass
TC_17 | Status Master | To check the fields in view option |  |  | It should display status, remark, is active, updated by and updated at fields. | display only sr no., status and actions option. | Fail |  | Pass
solved
TC_18 | Status Master | To check if we click on add data data is added or not | 1.click on masters. |  | Data should be added in the status master. | Data not added. | Fail |  | Pass
2.click on status management.
3.enter value in the status field.
|  |  | 4.click on add button. |  |  |  |  | solved
TC_19 | Status Master | To check edit button is working or not. | 1.click on edit button. |  | It should be display edit department | edit is working | Pass
TC_20 | Status Master | To check all fields in edit are present or not. | 1.click on masters. |  | It should display status, remark, is active fields. | it display only status. | Fail |  | Pass
2.click on status master.
solved
TC_21 | Status Master | To check history option is present or not. |  |  | History master is used to view the changes in the status of the ticket. | history option is not present. | Fail | solved | Pass
TC_22 | Status Master | To check delete button is working or not. |  |  | Delete button deletes the particular department | delete button not working | Fail |  | Pass
solved
TC_23 | Status Master | To check fields in the add option are mandatory or not | 1.click on masters. |  | The fields in the add button should mandatory | the fields are not mandatory | Fail |  | Pass
2.click on department management
|  |  | 3.click on add button. |  |  |  |  | solved
TC_24 | Status Master | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_25 | Status Master | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_26 | Employee Master | To check employee management is present or not. | 1.click on masters. |  | It should display employee management option after clicking on masters. | As Expected | pass
2.click on employee management
TC_27 | Employee Master | To check if click on employee management it redirects or not. |  |  | It should redirects to employee master page. | As Expected | pass
TC_28 | Employee Master | To check add employee is working or not. | 1.click on masters. |  | After clicking on add employee it displays employee details | Add Employee is not working | Fail |  |  | pass
2.click on employee management.
TC_29 | Employee Master | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_30 | Employee Master | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_31 | Employee Master | To check click on employee management employee data is display or not | 1.click on masters. |  | It should be display employee master page with employee data. | Employee data not display. | fail |  | pass
2.click on employee management.
TC_32 | Role master | To check role management is present or not. | 1.click on masters. |  | It should be display role master. | As Expected | pass
2.click on role management.
TC_33 | Role master | To check if click on role management it redirects or not. | 1.click on masters. |  | After clicking on role management it redirects to role master page. | As Expected | pass
2.click on role management.
TC_34 | Role master | To check add data is working or not. | 1.click on masters. |  | It should display field details which we have add | add button not working | Fail | solved | Pass
2.click on role management.
3.click on add button.
TC_35 | Role master | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_36 | Role master | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_37 | Role master | To check edit button is working or not. | 1.click on masters. |  | It should display edit page | edit button is not working. | Fail |  | Pass
2.click on role management.
3.click on edit button.
TC_38 | Role master | To check delete button is working or not. |  |  | It deletes the particular role. | delete button not working | Fail | solved | Pass
TC_39 | Role master | To check view in the role master page. |  |  | It should display role master data of all roles. | displays role master data. | Pass
TC_40 | Navigation drawer | To check logo is present or not. |  |  | It should display logo of techneai and the word techneai | another logo is present | Fail | 2021-12-07 | Pass
solved
TC_41 | Navigation drawer | To check pages are present or not. |  |  | It should display pages | As Expected | pass
TC_42 | Navigation drawer | To check if click on any page it navigate to particular page or not. |  |  | It should navigate to particular page. | As Expected | pass
TC_43 | Navigation drawer | To check whether toggle is present or not. |  |  | It should display toggle. | As Expected | pass
TC_44 | Navigation drawer | To check if click on toggle then it hides navigation drawer or not |  |  | After click on toggle it hides navigation drawer. | Toggle button is not clickable. | Fail | solved | Pass
TC_45 | Search Bar | To check whether seaarch bar is present or not |  |  | Search bar should be display. | As Expected | Pass
TC_46 | Search Bar | To check search bar is working or not |  |  | It used to search tickets, projects and worklists. | Search bar is not working. | Fail |  | Pass
solved
TC_47 | Profile Content | To check profile content is present or not |  |  | It shows profile content | As Expected | Pass
TC_48 | Profile Content | To check profile content consists of profile picture, name and designation |  |  | It should displays profile picture of user, name and designation. | It displays profile picture, name. It does not show designation. | Fail |  | Pass
solved
TC_49 | Profile Content | To check log out option is available or not after clicking on profile |  |  | After clicking on profile it should display the log out option | As Expected | Pass
TC_50 | Notification bell | To check notification bell is present or not |  |  | Notification bell should be present in dashboard. | As Expected | Pass
TC_51 | Notification bell | To check if click on notification bell it navigates to notification page or not. |  |  | clicking on notification bell it should redirects to the notification page. | As Expected | Pass
TC_52 | Notification bell | To check notification bell shows no of notifications or not. |  |  | It should display no of notifications | It shows only notification bell | Fail |  | Pass
solved
TC_53 | User Master | To check user management option is available or not. | 1.click on masters. |  | It should display user management option. | As Expected | Pass
2.click on user management.
TC_54 | User Master | To check if click on user management it redirects or not. | 1.click on masters. |  | After clicking on masters user master option should be display. | As Expected | Pass
2.click on user management.
TC_55 | User Master | To check whether we add data on clicking add button | 1.click on masters. |  | It should redirects to user master page for creating new user | As Expected | Pass
2.click on user management.
3.enter value
4.click on add user button
TC_56 | User Master | To check edit button is working or not. | 1.click on masters. |  | It should display edit user details | It displays profile details | Fail |  | Pass
2.click on user master
3.click on edit button.
solved
TC_57 | User Master | To check all fields in edit are present or not. | 1.click on masters. |  | It should display edit user details page with all the fields. | It displays profile details | Fail | solved | Pass
2.click on user management.
3.click on edit button.
TC_58 | User Master | To check mandatory fields are showing or not. |  |  | It should display mandatory fields (asterisk symbol) | Mandatory fields are not present. | Fail |  | Pass
solved
TC_59 | User Master | To check view is available or not. |  |  | It should display data of particular user. | It displays data of user but some fields are remaining. | Fail | solved | Pass
TC_60 | User Master | To check the fields in edit option |  |  | It should display edit user page. | It displays user profile details. | Fail |  | Pass
solved
TC_61 | User Master | To check history option is present or not. |  |  | History master is used to view the changes in the particular user | history option is not present. | Fail | solved | Pass
TC_62 | User Master | To check delete button is working or not. |  |  | Delete button deletes the particular user | delete button not working | Fail |  | Pass
solved
TC_63 | User Master | To check notification icon is present or not. |  |  | There should be notification icon | As Expected | Pass
TC_64 | User Master | To check click on notification icon pop up box for activity is open or not. |  |  | After click on notification icon pop up box should display. | As Expected | Pass
TC_65 | User Master | To check fields in the create user page after clicking on add user. | 1.click on masters. |  | It displays full name, user name, email id, contact no, department, gender, address, city like fields. | All fields are not there. | Fail |  | Pass
2.click on user management.
3.click on add user.
solved
TC_66 | User Master | To check fields are mandatory or not in create user page. | 1.click on masters. |  | mandatory fields should be shown using asterisk symbol. | Mandatory fields are not present. | Fail |  | Pass
2.click on user management.
3.click on add user.
solved
TC_67 | User Master | To check user is created or not. |  |  | User should be added in the user master page. | User not added | Fail |  | Pass
solved
TC_68 | User Master | To check create button is working or not. |  |  | After clicking on create button user should be added | create button not working | Fail |  | Pass
solved
TC_69 | User Master | To check cancel button is working or not. |  |  | After clicking on cancel button back to the user master page. | cancel button not working | Fail |  | Pass
solved
TC_70 | User Master | To check contact no field in the create user |  |  | Contact no should accepts the 10 digit number. | It accepts more than 10 digit number | Fail |  | Pass
solved
TC_71 | User Master | To check fields in the view user master page are correct or not |  |  | It should display view of all users with full name, username, mailid, contact no, department, designation, gender, address, city, state, country, pincode, profile picture, password, remark, is active, updated by, updated at fields. | It displays only sr, name and actions. | Fail |  | Pass
solved
TC_72 | Your Tickets | To check tickets tab is present or not |  |  | Tickets tab should display. | As Expected | pass
TC_73 | Tickets | To check tickets tab contains the total, unsolved, progress and finished tickets or not. |  |  | It should contains total tickets, unsolved tickets, progress tickets and finished tickets. | Tickets tab contains ticket management and your tasks. | Fail | solved | Pass
TC_74 | Tickets | To check if click on tickets tab ticket management is present or not. |  |  | there should beoption of ticket management | As Expected | pass
TC_75 | Tickets | To check after clicking on ticket management it redirects or not. | 1.click on masters. |  | It should display ticket master page | not redirects to ticket master page. | Fail |  | Pass
2.click on ticket management.
solved
TC_76 | Tickets | To check new ticket button is working or not | 1.click on masters. |  | It should displays create ticket page after clicking on new ticket button. | new ticket button is working | pass
2.click on ticket management.
3.click on new ticket.
TC_77 | Tickets | To check tickets page contains all fields or not. |  |  | It should display tickets page which contains naviagtion drawer, search bar, home button, notification bell, profile content. | all fields are present but home button are not there | Fail |  | Pass
solved
TC_78 | Tickets | To check if click on new ticket then create page consists of fields to adding new ticket. |  |  | It should display all fields contains ticket id, type of issue, actual user, actual date, department, expected date, file upload, priority, description, submit, cancel. | It contains ticket id, type of issue, priority, description, tikcet date, department, user, submit and cancel. Actual user, actual date, expected date, file upload are missing. | Fail |  | Pass
solved
TC_79 | Tickets | To check ticket date accept correct date or not. |  |  | The date should be auto generated. | It accepts any date. | Fail |  | Pass
solved
TC_80 | Tickets | To check department in the create ticket page |  |  | Department contains the dropdown which consists of department names. | department names are not present. | Fail |  | Pass
solved
TC_81 | Tickets | To check priority field in the create ticket page |  |  | Priority should be display in radio buttons with priority values like high, medium, etc. | Priority contains dropdown | Fail |  | Pass
solved
TC_82 | Tickets | To check mandatory fields are showing or not. |  |  | mandatory fields should be shown using asterisk symbol. | the fields are not mandatory | Fail |  | Pass
solved
TC_83 | Tickets | To check submit button is working or not. |  |  | After click on submit button ticket is added. | submit button not working | Fail |  | Pass
solved
TC_84 | Tickets | To check cancel button is working or not. |  |  | After clicking on cancel button it redirects to the ticket master page | cancel button is working | pass
TC_85 | Tickets | To check home button is present or not in all managements page. |  |  | There is home button which is redirects to the hme page. | Home button is not present. | Fail |  | Pass
solved
TC_86 | Dashboard | To check dashboard contains all fields or not. |  |  | It contains naviagtion drawer which contains logo, dashboard, projects like tabs | As Expected | pass
TC_87 | Dashboard | To check dashboard consists of tickets and worklists count. |  |  | It should display the count of tickets and worklists. | nothing shows on the dashboard. | Fail |  | Pass
solved
TC_88 | Dashboard | To check if click on sign in button it redirects to the home page or not. |  |  | Home page should be open. | As Expected | pass
TC_89 | Your task | To check your tasks tab |  |  | After clicking on your task tab the tasks should be display | no data is present. | Fail |  | Pass
solved
TC_90 | Communication Master | To check communication management is present in masters or not. | 1.click on masters and observe. |  | After clicking on masters Department management option should be display. | As Expected | Pass | 2021-12-18
TC_91 | Communication Master | To check if click on communication management it redirects or not. | 1.click on masters. |  | It should redirects to communication master page. | As Expected | Pass
2.click on communication management
TC_92 | Communication Master | To check whether add user button is working or not. | 1.click on masters. |  | Add user button should work properly | As Expected | Pass
2.click on communication management.
TC_93 | Communication Master | To check if click on add user button it redirects or not |  |  | After clicking on add user button it redirects to communication details page | As Expected | Pass
TC_94 | Communication Master | To check fields in the communication details page |  |  | communication type, subject and body this fields should be available to add new user | As Expected | Pass
TC_95 | Communication Master | To check data is added or not. | 1. click on add user button. |  | new user should be created | As Expected | Pass
2.enter all fields.
3. click on create button
TC_96 | Communication Master | To check create button is working or not. |  |  | Create button should be work properly | As Expected | Pass
TC_97 | Communication Master | To check cancel button is working or not. |  |  | After clicking on cancel button back to the communication master page. | As Expected | Pass
TC_98 | Communication Master | To check edit button is working or not. |  |  | After click on edit button it redirects to the edit page | It redirects user profile page | Fail |  | Pass
solved
TC_99 | Communication Master | To check delete button is working or not. |  |  | After click on delete button the related data should be deleted. | delete button not working | Fail |  | Pass
solved
TC_100 | Communication Master | To check communication type field accepts only characters |  |  | Communication type field accepts only characters | it accepts numeric values | Fail |  | Pass
solved
TC_101 | Communication Master | To check subject field accepts only characters |  |  | Subject field accepts only characters | it accepts numeric values | Fail |  | Pass
solved
TC_102 | Communication Master | To check body field accepts only characters |  |  | Body field accepts only characters | it accepts numeric values | Fail |  | Pass
solved
TC_103 | Communication Master | To check newly created data present first or not |  |  | Newly added data should be present first | newly added data is at last | Fail |  | Pass
solved
TC_104 | Communication Master | To check duplicate data is added or not |  |  | duplicate data should not added | duplicate data is added | Fail |  | Pass
solved
TC_105 | Communication Master | To check mandatory fields are showing or not. |  |  | mandatory fields should be shown using asterisk symbol. | Mandatory fields are not present. | Fail |  | Pass
solved
TC_106 | Country Management | To check country management option is available or not | 1.click on masters and observe. |  | Country management tab should be present in the masters | As Expected | Pass
TC_107 | Country Management | To check if click on country management it redirects or not | 1.click on masters |  | After click on country management it redirects to the country master page | As Expected | Pass
TC_108 | Country Management | To check country master page shows added data |  |  | Country master page should contains added data | nothing shows on the country master page | Fail |  | Pass
solved
TC_109 | Country Management | To check country is added or not | 1.enter value in the country name field. |  | Country should be added | Country not added | Fail |  | Pass
2.click on add button
solved
TC_110 | Customer Master | To check Customer management tab is present or not | 1.click on customer management |  | Customer Management option should be present | As Expected | Pass
TC_111 | Customer Master | To check when click on customer management it redirects or not | 1. click on customer management |  | After click on customer management it should redirects to the customer master page | As Expected | Pass
TC_112 | Customer Master | To check Add customer button is working or not | 1.click on customer management |  | After click on add customer button it redirects to the customer master create page | As Expected | Pass
2.click on add customer button
TC_113 | Customer Master | To check create button is working or not. |  |  | After click on create button data should be added | Data not added. | Fail |  | Pass
solved
TC_114 | Customer Master | To check all fields in the customer master page |  |  | Customer master page contains customer type, contact no, email id fields. | As Expected | Pass
TC_115 | Customer Master | To check cancel button is working or not. |  |  | After click on cancel button it redirects to the customer page | As Expected | Pass
TC_116 | Customer Master | To check edit button is working or not. | 1.click on masters |  | After click on edit button it redirects to the edit page | edit button is not working. | Fail |  | Pass
2.click on customer management
|  |  | 3.click on edit button. |  |  |  |  | solved
TC_117 | Customer Master | To check delete button is working or not. | 1.click on masters |  | After click on delete button the related data should be deleted. | delete button not working | Fail |  | Pass
2.click on customer management
|  |  | 3.click on delete button. |  |  |  |  | solved
TC_118 | Customer Master | To check data is added or not. |  |  | data should be added | Data not added. | Fail |  | Pass
solved
TC_119 | Designation Master | To check designation management tab is present or not | 1.click on masters and observe. |  | Designation management option should be present in the masters tab | As Expected | Pass
TC_120 | Designation Master | To check if click on designation management it redirects or not | 1.click on designation management |  | After clicking on designation management tab it redirects to the designation page. | As Expected | Pass
2.observe
TC_121 | Designation Master | To check Add designation button is working or not | 1.click on designation management |  | Add designation button should work properly. | As Expected | Pass
2.click on add designation button
TC_122 | Designation Master | To check if click on add designation button it redirects or not | 1.click on designation management |  | After click on add designation button it redirects to the designation/create page | As Expected | Pass
2.click on add designation button
TC_123 | Designation Master | To check data is added or not. |  |  | Data shouldbe added | As Expected | Pass
TC_124 | Designation Master | To check fields in the designation/create page |  |  | All fields should be present | As Expected | Pass
TC_125 | Designation Master | To check create button is working or not. |  |  | After click on create button data should be added | Data not added. | Fail |  | Pass
solved
TC_126 | Designation Master | To check cancel button is working or not. |  |  | After click on cancel button it should redirects to the designation page | cancel button not working | Fail |  | Pass
solved
TC_127 | Designation Master | To check designation field accepts right value or not | 1.click on masters. |  | designation field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail |  | Pass
2.click on designation management
3.click on add designation
solved
TC_128 | Designation Master | To check remark field accepts right value or not | 1.click on masters. |  | remark field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail |  | Pass
2.click on designation management
|  |  | 3.click on add designation |  |  |  |  | solved
TC_129 | Designation Master | To check designation field accepts blank value or not | 1.click on masters. |  | designation field accepts characters, numbers, special characters. | it accepts blank value | Fail |  | Pass
2.click on designation management
|  |  | 3.click on add designation |  |  |  |  | solved
TC_130 | Designation Master | To check remark field accepts blank value or not | 1.click on masters. |  | remark field accepts characters, numbers, special characters. | it accepts blank value | Fail |  | Pass
2.click on designation management
3.click on add designation
solved
TC_131 | Designation Master | To check fields are mandatory or not. | 1.click on masters. |  | Fields should be mandatory | Mandatory fields are not present. | Fail |  | Pass
2.click on designation management
3.click on add designation
solved
TC_132 | Designation Master | To check newly added data | 1.click on masters. |  | Newly added data should be present first | newly added data is at last | Fail |  | Pass
2.click on designation management
|  |  | 3.click on add designation |  |  |  |  | solved
TC_133 | Designation Master | To check duplicate data is added or not |  |  | duplicate data should not added | duplicate data is added | Fail |  | Pass
solved
TC_134 | Menu master | To check menu management tab is present or not | 1.click on masters and observe. |  | Menu management option should be present in the masters tab | As Expected | Pass
TC_135 | Menu master | To check if click on menu management it redirects or not | 1.click on menu management |  | After clicking on menu management tab it redirects to the menu page. | As Expected | Pass
2.observe
TC_136 | Menu master | To check Add menu button is working or not | 1.click on menu management |  | Add menu button should work properly. | As Expected | Pass
2.click on add menu button
TC_137 | Menu master | To check if click on add menu button it redirects or not | 1.click on menu management |  | After click on add menu button it redirects to the menu/create page | As Expected | Pass
2.click on add menu button
TC_138 | Menu master | To check data is added or not. |  |  | Data should be added | As Expected | Pass
TC_139 | Menu master | To check fields in the menu/create page |  |  | All fields should be present | As Expected | Pass
TC_140 | Menu master | To check create button is working or not. |  |  | After click on create button data should be added | As Expected | Pass
TC_141 | Menu master | To check cancel button is working or not. |  |  | After click on cancel button it should redirects to the designation page | As Expected | Pass
TC_142 | Menu master | To check menu name field accepts right value or not | 1.click on masters. |  | menu field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail |  | Pass
2.click on menu management
|  |  | 3.click on add menu |  |  |  |  | solved
TC_143 | Menu master | To check menu type field accepts right value or not | 1.click on masters. |  | menu type field accepts characters, numbers, special characters. | if we enter all numbers it accepts | Fail |  | Pass
2.click on menu management
3.click on add menu
solved
TC_144 | Menu master | To check menu name field accepts blank value or not | 1.click on masters. |  | menu type field accepts characters, numbers, special characters. | it accepts blank value | Fail |  | Pass
2.click on menu management
|  |  | 3.click on add menu |  |  |  |  | solved
TC_145 | Menu master | To check menu type field accepts blank value or not | 1.click on masters. |  | menu type field accepts characters, numbers, special characters. | it accepts blank value | Fail |  | Pass
2.click on menu management
3.click on add menu
solved
TC_146 | Menu master | To check fields are mandatory or not. | 1.click on masters. |  | Fields should be mandatory | Mandatory fields are not present. | Fail |  | Pass
2.click on menu management
|  |  | 3.click on add menu |  |  |  |  | solved
TC_147 | Menu master | To check newly added data | 1.click on masters. |  | Newly added data should be present first | newly added data is at last | Fail |  | Pass
|  |  | 2.click on menu management |  |  |  |  | solved
3.click on add menu
TC_148 | Menu master | To check duplicate data is added or not |  |  | duplicate data should not added | duplicate data is added | Fail |  | Pass
solved
TC_149 | Tenant Master | To check Tenant management tab is present or not | 1.click on masters and observe. |  | Tenanat management option should be present in the masters tab | As Expected | Pass
TC_150 | Tenant Master | To check if click on Tenant management it redirects or not | 1.click on tenant management |  | After clicking on tenant management tab it redirects to the menu page. | As Expected | Pass
2.observe
TC_151 | Tenant Master | To check Add tenant button is working or not | 1.click on tenant management |  | Add tenant button should work properly. | As Expected | Pass
2.click on add tenant button
TC_152 | Tenant Master | To check if click on add tenant button it redirects or not | 1.click on tenant management |  | After click on add tenant button it redirects to the tenant/create page | As Expected | Pass
2.click on add tenant button
TC_153 | Tenant Master | To check data is added or not. |  |  | Data should be added | Data not added. | Fail |  | Pass
solved
TC_154 | Tenant Master | To check fields in the tenant/create page |  |  | All fields should be present | As Expected | Pass
TC_155 | Tenant Master | To check create button is working or not. |  |  | After click on create button data should be added | create button not working | Fail |  | Pass
solved
TC_156 | Tenant Master | To check cancel button is working or not. |  |  | After click on cancel button it should redirects to the tenant page | cancel button not working | Fail |  | Pass
solved
TC_157 | Employee Master | To check mandatory fields are showing or not. | 1.click on masters |  | mandatory fields should be shown using asterisk symbol. | Mandatory fields are not present. | Fail |  | Pass
2.click on employee management
3.click on add employee button
solved
TC_158 | Ticket type master | verify that ticket type master option is available in home page or not. |  |  | ticket type master option should available in home page.
TC_159 | Ticket type master | verify that if click on add button it redirects to add data page or not. |  |  | add button should redirects to add data page.
TC_160 | Ticket type master | verify that add data button is working or not |  |  | add data button should work properly.
TC_161 | Ticket type master | to check fields in the add data option is correct or not |  |  | when click on add data option all fields should be present.
TC_162 | Ticket type master | to check mandatory fields are present in add data page or not |  |  | mandatory fields should be available.
TC_163 | Ticket type master | to check view data option is available or not to view the data in the ticket type master. |  |  | view data option should be there.
TC_164 | Ticket type master | to check fields in the view data option. |  |  | when click on view data option all fields should be present.
TC_165 | Ticket type master | To check view data option contains type, remark, is active, updated by, updated at fields. |  |  | view data option should contains type, remark, is active, updated by and updated at fields.
TC_166 | Ticket type master | to check edit option is working or not |  |  | edit option should be work properly.
TC_167 | Ticket type master | to check fields in the edit option are correct or not. |  |  | after click on edit option all fields should be there.
TC_168 | Ticket type master | To check edit option contains type, remark and is active fields or not in the edit page. |  |  | edit option should contains type, remark and is active fields in the edit page.
TC_169 | Ticket type master | to check history master contains type, remark, is active, updated at, updated by, ip address, user agent and created at fields are present or not. |  |  | history master should contains type, remark, is active, updated at, updated by, ip address, user agent and created at fields.
TC_170 | Dashboard | to check main view of dashboard consists of worklist pending and worklist completed on the priority basis |  |  | pending worklists and completed worklists should be there on the priority basis.
TC_171 | Navigation drawer | To check navigation drawer consists of techneai logo, dashboard, projects, tickets, worklists, clients, employees, masters tab or not. |  |  | navigation drawer should contains techneai logo, dashboard, projects, tickets, worklists, clients, employees, masters tab.
TC_172 | Dashboard | To check dashboard consists of count of pending worklists, inprogress worklists, completed worklists and total worklists. |  |  | dashboard should contains count of pending worklists, inprogress worklists, completed worklists and total worklists.
TC_173 | Dashboard | To check dashboard consists of count of all tickets, unsolved tickets, in progress tickets and completed tickets. |  |  | dashboard should contains count of all tickets, unsolved tickets, in progress tickets and completed tickets.
TC_174 | Dashboard | to check pending worklists are highlighted with red color or not. |  |  | Pending worklists should be in red color
TC_175 | Dashboard | to check completed worklists highlighted with white color or not. |  |  | completed worklists should be in white color
TC_176 | Dashboard | to check dashboard have smaller view of the user or employee profile |  |  | smaller view of the user or employee profile should be present in dashboard.
TC_177 | Dashboard | to check profile consists of profile picture, user name and designation. |  |  | profile picture, user name and designation should be present in profile.
TC_178 | Dashboard | to check notification bell is present or not |  |  | notification bell should be present in dashboard.
TC_179 | Dashboard | to check notification bell displays number on the bell if any notification arises. |  |  | notification bell should contains number on the bell if any notification arises.
TC_180 | work list tab | to check work list tab is available in home page or not |  |  | worklist tab should be available in home page.
TC_181 | work list tab | to check worklists tab consists of pending, progress, completed and total worklists or not |  |  | pending worklists, progress worklists, completed worklists and total worklists should be present when click on worklists tab.
TC_182 | work list tab | to check pending worklists contains worklists which are pending |  |  | pending worklists should contains worklists which are pending.
TC_183 | work list tab | to check progress worklists contains worklists which are in work in progress |  |  | worklists which are work in progress should be present in progress worklists.
TC_184 | work list tab | to check completed worklists contains worklists which are completed |  |  | completed worklists should be present in completed worklists.
TC_185 | work list tab | to check total worklists contains worklists which are completed, pending and in progress |  |  | completed worklists, pending worklists and in progress worklists should be present in total worklists.
TC_186 | tickets tab | to check whether tickets tab is present in home page or not |  |  | tickets tab should be available in home page.
TC_187 | tickets tab | to check tickets tab consists of total tickets, unsolved, progress and finished tickets |  |  | total tickets, unsolved tickets, progress tickets and finished tickets should be present when click on tickets tab.
TC_188 | tickets tab | to check total tickets consists of unsolved, progress and finished tickets |  |  | unsolved tickets, progress tickets and finished tickets should be present in total ticekts.
TC_189 | tickets tab | to check unsolved tickets consists of all the unsolved tickets which are not yet opened |  |  | unsolved tickets which are not yet opened should be in unsolved tickets.
TC_190 | tickets tab | to check progress tickets consists of tickets which are in work in progress |  |  | tickets which are in work in progress should be present in progress tickets.
TC_191 | tickets tab | to check finished tickets consists of tickets which are solved. |  |  | tickets which are solved should be in finished tickets.
TC_192 | list view with search(expected solved date) | to check list view which consists of work lists which are pending and expected to be solved according to the solve date filter |  |  | pending worklists and worklists expected to be solved should be in list view.
TC_193 | list view with search(expected solved date) | to check pending worklists are highlighted with red color or not. |  |  | pending worklists should be highlighted in red color.
TC_194 | list view with search(expected solved date) | to check expected tickets to be solved are in white background color. |  |  | expected tickets to be solved should be in white background color.
TC_195 | list view with search(expected solved date) | to check worklists consists of following fields worklist id, subject, assigned person, hours left, expected date, status, action button and search bar. |  |  | worklists should have worklist id, subject, assigned person, hours left, expected date, status, action button and search bar this fields.
TC_196 | worklists -> worklist ID | to check worklist id denotes the id of the worklist or not. |  |  | worklist id should contains the id of the worklist.
TC_197 | worklist -> Subject | To check subject field contains the description of the worklist or not |  |  | subject field should contains the description of the worklist.
TC_198 | worklist -> Assigned | To check assigned field contains name and profile picture of the assigned person or not. |  |  | assigned field should contains name and profile picture of the assigned person.
TC_199 | worklist -> Hours left | To check hours left field contains hours and minutes left to finish that particular worklist / task. |  |  | hours left field should contains hours and minutes left to finish that particular worklist.
TC_200 | worklist -> created date | To check created date field contains date on which the worklist is created. |  |  | created date field should contains date on which the worklist is created.
TC_201 | worklist -> Status | To check status field contains status of the worklist is mentioned whether it is pending or in progress. |  |  | status field should contains status of the worklist whether it is pending or in progress.
TC_202 | worklist -> Actions | to check actions field contains view and edit options. |  |  | view and edit option should be in actions field.
TC_203 | worklist -> Actions | to check view option is working or not |  |  | view option should be work properly.
TC_204 | worklist -> Actions | to check edit option is working or not |  |  | edit option should be work properly.
TC_205 | worklist -> search bar | To check search bar is used to search the worklist by using id of the worklist. |  |  | worklist should be search by using id of the worklist.
TC_206 | worklist -> search bar | to check previous button redirects to the previous page of the worklists or not |  |  | previous button should redirects to the previous page of the worklists.
TC_207 | worklist -> search bar | to check next button redirects to the next page of the worklists or not |  |  | next button should redirects to the next page of the worklists.
TC_208 | Projects tab | to check projects tab is present in home page or not |  |  | project tab should be present in home page.
TC_209 | Projects tab | to check projects tab consists of navigation drawer, worklists tab, tickets tab, profile content, search bar same as dashboard. |  |  | navigation drawer, worklists tab, tickets tab, profile content, search bar should be available in tickets tab.
TC_210 | Projects tab | to check whether projects are designed in grid view or not. |  |  | projects should be designed in grid view.
TC_211 | Projects tab | to check tickets when created are assigned to the particular project by BA. |  |  | created tickets should assigned to the particular project by BA.
TC_212 | Projects tab | to check create project button is working or not. |  |  | create project button should work properly.
TC_213 | grid view of the projects | to check grid view contains details of projects in the grid view |  |  | grid view should have details of projects in the grid view.
TC_214 | grid view of the projects | to check grid view consists of following details project name, assigned person pictures, attached ticket number, assigned persons, time for the project, comments, action button to view and edit, status of project, time left to solve project |  |  | project name, assigned person picture, attached ticket number, assigned persons, time for the project these fields should be in grid view.
TC_215 | Projects -> Project Name | to check project name consists of name of the project with icon and picture is displayed. |  |  | name of the project with icon and picture should displayed in project name.
TC_216 | Projects -> Subject | To check subject field contains the subject of the project is mentioned or not. |  |  | Subject field should mentioned the subject of the project.
TC_217 | Projects -> Assigned Members | to check assigned members consists of pictures of assigned persons |  |  | pictures of assigned persons should be in assigned members.
TC_218 | Projects -> Assigned Members | to check assigned members consists of pictures of assigned persons |  |  | pictures of assigned persons should be in assigned members.
TC_219 | Projects -> Attach | To check attach field contains number of tickets are attached to that particular project or not. |  |  | attach field should contains number of tickets are attached to that particular project.
TC_220 | Projects -> Members | To check members field mentioned number of peoples assigned for particular project or not. |  |  | members field should mentioned the number of peoples assigned for particular project.
TC_221 | Projects -> Month | To check month field displays the total time taken for the completion of that particular ticket. |  |  | month field should displays total time taken for the completion of that particular ticket.
TC_222 | Projects -> Comments | To check comments field displays number of comments on that particular project. |  |  | Comments field should displays number of comments on that particular project.
TC_223 | Projects -> Status | To check status consists of status of the project (unsolved, progress, completed) and bar form depending on the percentage of the completion of project. |  |  | status should contains status of the project and bar form depending on the percentage of the completion of project.
TC_224 | Projects -> Days left | To check days left field mention the days left to complete that particular project. |  |  | Days left field should mention the days left to complete that particular project.
TC_225 | Projects -> Action | to check action field contains edit and view buttons. |  |  | action field should contains edit and view buttons.
TC_226 | list view of the tickets | to check list view of the tickets consists of ticket id, subject, assigned, hours left, created date, status, action button to view and edit the ticket |  |  | ticket id, subject, assigned, hours left, created date, status, action button to view and edit the ticket should be in list view.
TC_227 | list view of the tickets | to check search bar to search the ticket is present or not |  |  | search bar should be present in list view of tickets to search the ticekt.
TC_228 | list view of the tickets | to check previous and next buttons are present or not |  |  | previous and next buttons should be in list view of tickets page.
TC_229 | list view of the tickets | to check "add ticket" button is present or not |  |  | "add ticket" button should be present in list view of tickets page.
TC_230 | list view of the tickets -> ticket id | To check ticket id is displayed or not. |  |  | "ticket id" field should display id of the ticket.
TC_231 | list view of the tickets -> subject | To check whether subject field mentioned the subject of the ticket |  |  | "subject" field should mentioned the subject of the ticket.
TC_232 | list view of the tickets -> Assigned | to check assigned consists of name and profile picture of assigned person |  |  | name and profile picture of assigned person should be in assigned field.
TC_233 | list view of the tickets -> Hours left | to check hours and minutes left to finish that particular ticket |  |  | hours and minutes left to finish the particular ticket should be present in hours left field.
TC_234 | list view of the tickets -> Created date | to check created date on which the ticket is created |  |  | created date should be present in created date field when the ticket is created.
TC_235 | list view of the tickets -> Status | to check status consists of status of the ticket whether it is pending or in progress |  |  | status should contains status of the ticket whether it is pending or in progress.
TC_236 | list view of the tickets -> Action | to check action column consist of edit and view buttons. |  |  | edit and view buttons should be in action field.
TC_237 | list view of the tickets -> search bar | to check search bar to search the ticket by id of the ticket |  |  | search bar should be present in list view of ticekts to search the ticket by id of the ticket.
TC_238 | list view of the tickets -> previous | to check previous button redirects to the previous page of the ticket view |  |  | previous button should redirects to the previous page of the ticket view.
TC_239 | list view of the tickets -> next | to check next button redirects to the next page of the ticket view |  |  | mext button should redirects to the next page of the ticket view.
TC_240 | list view of the tickets -> add ticket | to check add ticket button is working or not |  |  | add ticket button should be working properly.
TC_241 | work lists | to check work lists page consists of navigation drawer, worklists tab, profile content, search bar same as dashboard. |  |  | navigation drawer, worklists tab, profile content, search bar should be present in worklists tab.
TC_242 | work lists | to check worklists are designed in the grid view |  |  | worklists should be designed in grid view.
TC_243 | work lists | to check worklists are the tasks assigned for particular ticket or not. |  |  | worklists should be the tasks assigned for particular ticket.
TC_244 | work lists | To check worklists are created in the tickets edit page or not. |  |  | worklists should be created in the tickets edit page.
TC_245 | grid view of the worklists | to check lists are viewed in grid view or not. |  |  | lists should be viewed in grid view.
TC_246 | grid view of the worklists | to check columns namely, inprogress, unsolved, completed are present or not |  |  | inprogress, unsolved, completed columns should be in grid view of the worklists.
TC_247 | grid view of the worklists | To check worklists can be viewed by using the drag motion to change the status of the worklists. |  |  | worklists should be viewed by using the drag motion to change the status of the worklists.
TC_248 | grid view of the worklists | to check fields in the grid are correct or not which is subject, ticket subject, id, assigned person, description, time left, priority |  |  | subject, ticket subject, id, assigned person, description, time left, priority these fields should be in grid.
TC_249 | view of worklists -> Subject | To check the subject field contains the subject of the worklist along with id |  |  | "Subject" field should mentioned the subject of the ticket along with id.
TC_250 | view of worklists -> Description | To check "description" field contains the descrition of the worklist |  |  | "description" field should mentioned the description of the worklists.
TC_251 | view of worklists -> Time | To check "time" field mentioned the time left for that particular ticket. |  |  | "time" field should mentioned the time left for that particular ticket.
TC_252 | view of worklists -> Assigned | To check "assigned" field display assigned persons through pictures or not. |  |  | "Assigned" field should display assigned persons through pictures.
TC_253 | view of worklists -> Priority | to check priority of the worlists are correct or not which is very high, high, medium and low. |  |  | priority of the worklists should be very high, high, medium and low.
TC_254 | Ticket detail page | to check ticket detail page consists of navigation drawer, search bar, home button, notification bell and the profile content fields or not. |  |  | ticket detail page should contains navigation drawer, search bar, home button, notification bell and profile content.
TC_255 | Ticket detail page | to check if user clicks on eye button then view of the ticket is display or not. |  |  | user clicks on eye button the view of the ticket should be display.
TC_256 | Ticket detail page | To check view page consists of the following fields such as ticket id, edit button, status, created name, priority, description, type of issue, expected date, assign, images attached, files attached, chat/comments, play button, pause button and time left this fields or not. |  |  | view page should contains following fields such as ticket id, edit button, status, created name, priority, description, type of issue, expected date, asisgn, images attached, files attached, chat/comments, play button, pause button and time left.
TC_257 | Ticket detail page view -> Ticket ID | To check "Ticket ID" field generates the id automatically when user or BA selects the add ticket option. |  |  | "Ticket ID" field shoud generate id automatically.
TC_258 | Ticket detail page view -> Edit button | To check if click on "edit button" redirects to the editing page of the ticket. |  |  | When click on edit button it should redirects to the editing page of the ticket.
TC_259 | Ticket detail page view -> Status | To check "Status" field shows the status of the ticket or not. |  |  | "Status" field should shows the status of the ticket i.e. unsolved, inprogress or completed.
TC_260 | Ticket detail page view -> Created Name | to check "created name" field which contains name of the user who created ticket and their picture is present or not. |  |  | name of the user who created ticket and their picture should be in created name field.
TC_261 | Ticket detail page view -> Priority | To check priority of the ticket is mentioned or not in the "Priority" field. |  |  | priority of the ticket should be mentioned in the "Priority" field.
TC_262 | Ticket detail page view -> Description | To check "description" field contains the descrition of the ticket. |  |  | "Description" field should mentioned the description of the tickets when created.
TC_263 | Ticket detail page view -> Type of Issue | to check type of issue of ticket is mentioned or not in the "Type of Issue" field. |  |  | type of issue of ticket should be mentioned in the "Type of Issue" field.
TC_264 | Ticket detail page view -> Expected Date | to check expected date is auto calculated by system or not. |  |  | expected date should be auto calculated by system.
TC_265 | Ticket detail page view -> Assign | to check "assign" field shows the name of the assign person or not. |  |  | "assign" field should contains the name of the assign person.
TC_266 | Ticket detail page view -> Images Attached | to check images attached or not in the "Images Attached" field. |  |  | images should be attached in "images attached" field.
TC_267 | Ticket detail page view -> Images Attached | to check images are download or not by clicking on download button |  |  | clicking on download button images should be downloaded.
TC_268 | Ticket detail page view -> Files Attached | to check files attached or not in the "Files Attached" field. |  |  | all the files related to particular ticket should be attached in "files attached" field.
TC_269 | Ticket detail page view -> Files Attached | to check files are download or not by clicking on download button. |  |  | files should be downloaded when click on download button.
TC_270 | Ticket detail page view -> Comments | to check all the comments are displayed or not in the "Comments" field. |  |  | comments should be displayed in "comments" field.
TC_271 | Ticket detail page view -> Play button | to check play button is working or not when click on it. |  |  | play button should work properly when click on it.
TC_272 | Ticket detail page view -> Pause button | to check pause button is working or not when click on it. |  |  | pause button should work properly when click on it.
TC_273 | Ticket detail page view -> Time | to check time is auto calculated or not . |  |  | time should be auto calculated.
TC_274 | Ticket detail page view -> Time | to check time shows the time left to solve the particular ticket is correct or not. |  |  | time should shows the time left to solve the particular ticket.
TC_275 | Editing the ticket | to check if click on edit button it displays the following fields ticket id, attach file, comment, work log, history, buckets, time, play/pause, quit and graph are present or not. |  |  | if click on edit button it should displays ticket id, attach file, comment, worklog, history, buckets, time, play/pause, quit and graph.
TC_276 | Edit ticket -> Ticket ID | To check id of the ticket is auto generated or not in the "Ticket ID" Field. |  |  | ticket id should be auto generated in "Ticket ID" field.
TC_277 | Edit Ticket -> Attachments | to check files are attached or not in the "Attachments" field. |  |  | files should be attached in "attachments" field.
TC_278 | Edit Ticket -> Attachments | to check previously attached files are viewed or not. |  |  | previously attached files should be viewed.
TC_279 | Edit Ticket -> Comments | to check the comment section contains all the comments which can be use to view and comment. |  |  | comment section should contains all the comments which can be use to view and comment.
TC_280 | Edit Ticket -> Worklog | to check worklog shows the working time on ticket. |  |  | worklog should shows the working time on ticket.
TC_281 | Edit Ticket -> History | to check history column shows the history of the ticket or not. |  |  | history column should shows the history of the ticket.
TC_282 | Edit Ticket -> Buckets | to check buckets are designed according to the template selected. |  |  | Buckets should be designed according to the template selected.
TC_283 | Edit Ticket -> Worklists | to check worklists are created for respective department or not. |  |  | worklists should be created for respective department.
TC_284 | Edit Ticket -> Worklists | to check estimated time for worklists is mentioned or not. |  |  | estimated time for each worklists should be mentioned
TC_285 | Edit Ticket -> Checklists | to check check lists for each worklists are created for respective department or not. |  |  | checklists should be created for each worklists for respective department.
TC_286 | Edit Ticket -> Checklists | to check estimated time for checklists are mentioned or not. |  |  | estimated time for each checklists should be mentioned.
TC_287 | Edit Ticket -> Time left | to check time left for completion of the ticket is viewed or not. |  |  | time left for completion of the ticket should be viewed.
TC_288 | Edit Ticket -> Play button | to check play button is working or not when click on it to start the time. |  |  | if click on play button it should starts the time.
TC_289 | Edit Ticket -> Pause button | to check pause button is working or not when click on it to pause the time. |  |  | if click on pause button it should pause the button.
TC_290 | Edit Ticket -> Quit button | to check quit button is working or not when click on it to stop the timing. |  |  | if click on quit button it should stops the timing.
TC_291 | clients | to check clients are viewed in the clients page or not. |  |  | clients should be viewed in clients page.
TC_292 | clients | to check clients page consists of naviagtion drawer, search bar, home button, notification bell and the profile content are present or not. |  |  | naviagtion drawer, search bar, home button, notification bell and profile content should be present in clients page.
TC_293 | client profile | to check profile of the particular client is viewed or not. |  |  | profile of the particluar client should be viewed.
TC_294 | client profile | to check clients profile page consists of navigation drawer, search bar, home button, notification bell and the profile content fields or not. |  |  | navigation drawer, search bar, home button, notification bell and the profile content should be present in the clients page.
TC_295 | Employee | to check employees are viewed in employees page or not. |  |  | employees should be viewed in employees page.
TC_296 | Employee | to check employee page consists of navigation drawer, search bar, home button, notification bell and the profile content are present or not. |  |  | navigation drawer, search bar, home button, notification bell and profile content should be present in employee page.
TC_297 | Employee profile | to check profile of the particular employee is viewed or not. |  |  | profile of the particular employee should be viewed.
TC_298 | Employee profile | to check employee profile page consists of navigation drawer, search bar, home button, notification bell and the profile content are present or not. |  |  | navigation drawer, search bar, home button, notification bell and profile content should be present in employee profile page.
TC_299 | Selection of template | to check template page consists of following fields or not such as new ticket, reopen ticket, ticket id, type of issue, description, actual user, actual date, department, priority, attachment, expected date, template, bucket 1, bucket 2, bucket 1 remark , bucket 2 remark |  |  | new ticket, reopen ticket, ticket id, type of issue, description, actual user, actual date, department, priority, attachment, expected date, template, bucket 1, bucket 2, bucket 1 remark, bucket 2 remark this fields should be present in template page.
TC_300 | Selection of template -> New Ticket | to check new ticket button is working or not to raise a ticket. |  |  | new ticket button should work properly to raise a ticket.
TC_301 | Selection of template -> Reopen Ticket | to check reopen ticket button is working or not. |  |  | reopen ticket button should work properly.
TC_302 | Selection of template -> Ticket ID | To check "Ticket ID" field generates the id automatically. |  |  | "Ticket ID" field should generates id automatically.
TC_303 | Selection of template -> Type of Issue | to check type of issue of ticket is mentioned or not. |  |  | type of issue of ticket should be mentioned.
TC_304 | Selection of template -> Description | To check "Description" field contains the description of the ticket. |  |  | Description of the ticket should be mentioned in the "Description" field.
TC_305 | Selection of template -> Actual User | to check actual user option selects the user to raising the ticket is present or not. |  |  | actual user option should selects user to raising the ticket.
TC_306 | Selection of template -> Actual Date | to check actual date is automatically generated or not. |  |  | actual date should be automatically generated.
TC_307 | Selection of template -> Department | to check the department of the person who raising the ticket is selects or not. |  |  | department of the person who raising the ticket should be selected.
TC_308 | Selection of template -> Priority | To check the priority is selects or not which is very high, high, medium and low. |  |  | priority should be selected from dropdown which is very high, high, medium and low.
TC_309 | Selection of template -> Attachment | to check files are attached or not in the "Attachments" field. |  |  | files should be attached in "attachments" field.
TC_310 | Selection of template -> Expected Date | To check expected date of the ticket is selected using dropdown box. |  |  | expected date of the ticket should be selected.
TC_311 | Selection of template -> Template | To check template required is selected from the drop down menu. |  |  | Template required should be selected from the drop down menu.
TC_312 | Selection of template -> Bucket 1 | To check departments are selected which are used in the bucket 1 |  |  | Departments should be selected which are used in the bucket 1.
TC_313 | Selection of template -> Bucket 1 | To check names of the assigned persons are selected. |  |  | Names of assigned persons should be selected.
TC_314 | Selection of template -> Bucket 2 | To check departments are selected which are used in the bucket 2 |  |  | Departments should be selected which are used in the bucket 2.
TC_315 | Selection of template -> Bucket 1 remark | To check remark and selects assigned person in "bucket 1 remark" field. |  |  | Remark and assigned persons shold be selected.
TC_316 | Selection of template -> Bucket 2 remark | To check remark and selects assigned person in "bucket 2 remark" field. |  |  | Remark and assigned persons shold be selected.
TC_317 | Selection of template -> Comment Section | To check comment section is viewed by everyone or assigned users or assigned and tagged users. |  |  | Comment section should be viewed by everyone or assigned users or assigned and tagged users.
TC_318 | Gantt Chart | To check gantt chart is present or not. |  |  | gantt chart shoule be present.
TC_319 | Gantt Chart | To check status of the ticket is viewed in the gantt chart or not. |  |  | status of the ticket should be viewed in the gantt chart.
TC_320 | Gantt Chart | To check gantt chart describes list of activities and time scale . |  |  | gantt chart should describes the list of activities on left and time scale on top.
TC_321 | Gantt Chart | To check each activity is represented by bar or not. |  |  | each activity should be represented by bar.
TC_322 | Rating System | To check rating system is there or not. |  |  | rating system should be present.
TC_323 | Rating System | To check user review entire process and submit their feedback |  |  | User should review entire process and submit thier feedback and add thier feedback in written.
TC_324 | Reports | To check reports are generated or not. |  |  | reports should be generated.
TC_325 | Reports | To check following type of reports are generated or not - stage wise report, type wise report, entry department wise, user wise report, timeline report, gantt report. |  |  | stage wise report, type wise report, entry department wise report, user wise report, timeline report, gantt report should be generated.
TC_326 | Stage wise report | To check stage wise report describes in which stage the ticket is i.e. developing, testing etc. |  |  | stage wise report should describes in which stage the ticket is i.e. developing, testing, etc.
TC_327 | Type wise report | To check type wise report describes the type of the report whether it is in house development, software, hardware etc. |  |  | type wise report should describes the type of the report whether it is in house development, software, hardware etc.
TC_328 | Entry department wise report | To check entry department wise report describes the points assigned to particular department whether business analyst, administration support, hardware etc. |  |  | entry department wise report should describes the points assigned to particular department whether business analyst, administration support, hardware, etc.
TC_329 | User wise report | To check user wise report describes all the details related to all the tickets according to the users. |  |  | user wise report should describes all the details related to all the tickets according to the users.
TC_330 | Timeline report | To check timeline report describes the stage in timeline order i.e. development, tester, hardware etc. |  |  | timeline report should describes the stage in timeline order i.e. development, tester, hardware, etc.
TC_331 | Gantt Report | To check gantt report generates the graphical representation of the ticket. |  |  | gantt report should generates the graphical representation of the ticket.
TC_332 | From date | To check from date is correct or not when the ticket is raised. |  |  | from date should be correct when the ticket is raised.
TC_333 | To date | To check to date is correct or not when the ticket is raised. |  |  | to date should be correct when the ticket is raised.
TC_334 | Filter | To check filter selects type of reports or not. |  |  | filter should selects the type of reports.
TC_335 | Sub-fields | To check subfield selects business analyst, developer, tester, in house development, all the employees, etc. |  |  | sub field should selects business analyst, developer, tester, in house development, all the employees, etc.
TC_336 | General Report | To check general report contains following fields Ticket ID, type of issue, description, actual user, actual date, department, priority, expected date, template, level1, level 2, level 1 remark, level 2 remark, remark, entry user, status, expected solved date, sign off date, estimatedd date, external reference number, days after expected solved date, work log, assigned BA, Assigned developer, assigned tester or not. |  |  | general report should contains the following fields ticket id, type of issue, description, actual user, actual date, department, priority, expected date, template, level1, level 2, level 1 remark, level 2 remark, remark, entry user, status, expected solved date, sign off date, estimated date, external reference number, days after expected solved date, worklog, assigned BA, assigned developer, assigned tester.
TC_337 | Status Wise report | To check status wise report contains ticket ID, type of issue, description, actual user, actual date, department, expected date, template, level 1, level 2, entry user, status, expected solved date, assigned BA fields or not. |  |  | status wise report should contains ticket id, type of issue, description, actual user, actual date, department, expected date, template, level 1, level 2, entry user, status, expected solved date, assigned BA.
TC_338 | Type wise report | To check type wise report contains following fields or not such as - ticket ID, type of issue, description, actual user, actual date, department, expected date, template, level 1, level 2, entry user, status, expected solved date, assigned BA. |  |  | type wise report should contains ticket id, type of issue, description, actual user, actual date, department, expected date, template, level 1, level 2, entry user, status, expected solved date, assigned BA.
TC_339 | Entry department wise report | To check entry department wise report contains following fields or not such as - ticket ID, type of issue, description, actual user, actual date, department, expected date, template, level1, level2, entry usser, status, expected solved date, assigned BA. |  |  | entry department wise report should contains ticket id, type of issue, description, actual user, actual date, department, expected date, template, level 1, level 2, entry user, status, expected solved date, assigned BA.
TC_340 | User wise report | To check user wise report contains following fields or not ticket ID, type of issue, actual user, actual date, department, expected date, template, level1, level 2, entry user, status, expected solved date, assigned BA, sign off date, estimated date. |  |  | user wise report should contains ticket id, type of issue, actual user, actual date, department, expected date, template, level 1, level 2, entry user, stataus, expected solved date, assigned BA, sign off date, estimated date.
TC_341 | Timeline report | To check timeline report contains following fields or not such as - ticket ID, type of issue, description, actual user, actual date, department, expected date, template, level1, level2, entry user, status, expected solved date, assigned BA, estimated date, days after expected solved date and worklog. |  |  | timeline report should contains ticket id, type of issue, description, actual user, actual date, department, expected date, template, level 1, level 2, entry user, status, expected solved date, assigned BA, estimated date, days after expected solved date and worklog.
TC_ | login | to check if entering valid email address and password then login is successfully or not. | 1. go to url |  | Login should be successfully done. | As Expected | Pass
2. enter valid email address
3.enter valid password.
4,click on sign in
| login | to check if user enters invalid email address and valid password then login is done or not |  |  | invalid email address message should be display. | As Expected | Pass
| login | to check if user enters valid email address and invalid password then login is done or not. |  |  | invalid password message should be display. | As Expected | Pass
| login | to check if user enters invalid email address and password then login is done or not. |  |  | error message should be display. | no error message is display. | Fail
| sign in | to check if entering valid data and click on sign in button then it redirects or not. |  |  | entering valid data and click on sign in button then dashboard should be open. | dashboard not open | Fail
| remember me | to check whether remember me button is there or not. |  |  | remember me button should be there. | remember me button is not there | Fail
| forgot password | to check forgot password link is present or not |  |  | forgot password link should be present | forgot password button is not there | Fail
| Sign in | to check sign in button is working or not. |  |  | click on sign in button login should be done successfully | Sign up button is not there | Fail
| login page | to check whether logo is present or not. |  |  | techneai logo should be present in login page. | no logo present in login page | Fail