## Sheet1
TT9027 - Scope Details
Module | Sub Module | Create Fields
Masters | User Master
Customer Master
Country Master
State Master
City Master
Designation Master
Department Master
Role Master
Status Master
Customer Type Master
Dynamic Form
Query Type Master
Template Master
Customer Mapping
Dynamic Form Dropdown
Ticket | My Ticket
Create Ticket

## Sheet2
[6 empty] | solved date |  | EFD | Remark
15 | UM | TT_UM_15 | 3 Low | Functional | 4.WhatsApp Number : Editable and allows user to enter more than 10 digits. It is accepting all ten digits as ‘0’. Expected result - it should accept 10 digits - 1 to 9 digit and zero can be accepted at last digit. |  |  | 2023-02-13 | Resolved
29 | UM | TT_UM_29 | 3 Low | Functional | While trying to change the department at edit user screen , system is not allowing . (No action reaction seen after click on submit button) |  |  | 14/2/2023
1. select user for Edit
2. change the department
3. click on Submit button
61 | MT | TT_MT_61 | 1 High | Functional | When basket owner have access to play and pause the task of assigned users then when it is group task he is not able to play and pause the same task. |  | Priyanka
62 | MT | TT_MT_62 | 1 High | Functional | 5. When basket owner has created task for 3 people and he is not part of that task still he can play the and pause the task. It is expected that he should not be having authority to play the task or group activity of another user. He should be able to review task timings. |  | Priyanka
75 | MTB | TT_MTB_75 | 2 Medium | Functional | While creating basket start date field is accepting greater date than end date. Need validation to start date and end date. |  | Priyanka | 14/02/2023 | Resolved
76 | MTB | TT_MTB_76 | 2 Medium | Functional | Basket Name, select user, start date and end date are mandatory fields are not having mandatory star mark. |  | Priyanka | 14/02/2023 | Resolved
77 | MTB | TT_MTB_77 | 2 Medium | Functional | Added baskets are not arranged properly |  | Priyanka
When screens size gets reduces basket alignment not arranged properlysqueeze
78 | MTT | TT_MTT_78 | 2 Medium | Functional | While creating task end date picker should not be accept smaller date than start date. | 14/02/2023 | Priyanka | 14/02/2023 | Resolved
82 | MTT | TT_MTT_82 | 2 Medium | Functional |  |  | Priyanka
90 | MTT | TT_MTT_90 | 2 Medium | Functional | “from” and “to date” field need validation. To date field accepts smaller date than from date. | 14/02/2023 | Priyanka | 14/02/2023 | Resolved
94 | UTR | TT_UTR_94 | 2 Medium | Functional | filtered record doesn’t export all data is exported in file. | 14/02/2023 | Priyanka | 14/02/2023 | resolved
108 | UM | TT_UM_108 | 3 Low | Functional | Contact number Validation is not applied for WhatsApp Number . Contact number validation should reflect for WhatsApp Number |  | Preeti | 14/02/2023 | Resolved
111 | UM | TT_UM_111 | 2 Medium | Functional | Address Field is not accepting " Enter" key( new line). it should accept. | 14/02/2023 | Preeti | 14/02/2023 | Resolved
113 | CT | TT_CT_113 | 2 Medium | Functional | For Bulk uploading though default department populated , still system throws error " please select department and Query Type" . User has to select the value from dropdown inspite of one or many department. |  | Preeti
114 | CT | TT_CT_114 | 3 Low | Functional | For Bulk upload, user has to click 1st on 'Generate Bulk Format' and then click on 'Download file' then only user can proceed for Bulk uploading. |  | Preeti
Can we omit the 'Generate Bulk format' click on step.
116 | VR | TT_VR_116 | 2 Medium | Functional | "Complted at" column is not present in variance report grid still it is displayed in downloaded file. |  |  |  | Resolved
117 | RP | TT_RP_117 | 1 High | Functional | while selecting user in "select user" dropdown it redirects to blank page. | 14/02/2023 | Priyanka | 15/02/2023 | Resolved
121 | RP | TT_RP_121 | 1 High | functional | when we selects user in "select user" field and clicked on search it doesnt display report. | 14/02/2023 | priyanka | 15/02/2023 | resolved
122 | RP | TT_RP_122 | 2 Medium | functional | "from date", and "to date" fields are mandatory it is not having mandatory star mark. and if user left any field empty it doesnt display error warning message. | 14/02/2023 | priyanka | 15/02/2023 | Resolved
123 | MT | TT_MT_123 | 2 Medium | functional | when we edit task it doesnt load proper "Assign to user" and dependent task field. | 14/02/2023 | priyanka | 15/02/2023 | Resolved
124 | RP | TT_RP_124 | 2 Medium | functional | user names should be dislay in ascending order in "Select user" dropdown. | 14/02/2023 | priyanka | 16/02/2023 | resolved
125 | RP | TT_RP_125 | 2 Medium | functional | without selecting "select user" if filter the records according to date user names are not displayed in proper order. |  | priyanka | 16/02/2023 | Resolved
126 | MT | TT_MT_126 | 2 Medium | functional | not working proper while play pause the group activity. |  | priyanka
127 | MT | TT_MT_127 | 2 Medium | functional | when it is "group tasks" or "group activity" it is not arrranged properly. |  | priyanka
128 | MT | TT_MT_128 | 2 Medium | functional | when user have multiple baskets at a time different "group activities" are playing from "differnet baskets" of same user. |  | priyanka
129 | MT | TT_MT_129 | 2 Medium | functional | When user has created task and after it is edited with "group activity" play pause functionality is not working properly. |  | priyanka
130 | MT | TT_MT_130 | 2 Medium | functional | when "basket owner" is not part of specific task he should not be having authority to send the regularization request. |  | priyanka
133 | CB | TT_CB_133 | 3 Low | UI | Send button location is different from Edit view. |  | Priyanka | 16/02/2023
134 | CB | TT_CB_134 | 2 Medium | Functional | Mention text displays Twice |  | Preeti
135 | CB | TT_CB_135 | 3 Low | Functional | Text is displayed in blue colour, expected to display in black colour |  | Preeti
136 | MT | TT_MT_136 | 1 High | Functional | While creating the ticket it has ben observed that Ticket assigned to deactive user and further journey is not progressing. |  | Amreen
140 | MT | TT_MT_140 | 1 High | Functional | "planner" option should not be visible for completed tasks. | 14/02/2023 | Priyanka | 16/02/2023 | resolved
141 | MT | TT_MT_141 | 2 Medium | Functional | user can enter the back date in planner."date" field should be disable. | 14/02/2023 | Priyanka | 16/02/2023 | resolved
142 | MT | TT_MT_142 | 2 Medium | Functional | If in planner "divided task hours" and "scheduled task hours" are not equal still task is getting updated. it doesnt display warning message. | 14/02/2023 | Priyanka | 17/02/2023 | Resolved
143 | MT | TT_MT_143 | 2 Medium | Functional | If it is group task and I have edited "Assigned user" and assigned same user in planner it doesnt display any error message. |  | Priyanka | 17/02/2023
144 | CSM | TT_CSM_144 | 2 Medium | Functional | previously selected users are not displaying in edit customer mapping. |  | priyanka
145 | CSM | TT_CSM_145 | 2 Medium | Functional | Department wise usernames are not displaying in "select user" field. |  | priyanka
146 | CSM | TT_CSM_146 | 2 Medium | Functional | User is not able to update users in "select user" field. |  | priyanka
147 | CSM | TT_CSM_147 | 2 Medium | Functional | while creating customer mapping even though mapping is not done it displays successful message"Record inserted." |  | priyanka
148 | CT | TT_CT_148 | 2 Medium | Functional | Passing Authority should receive notification if any user of the same department creates ticket the and that ticket should come under his unpassed ticket list. |  | Amreen
149 | NTF | TT_NTF_149 | 2 Medium | Functional | When passing authority passes a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has passed #TicketId" |  | Amreen
150 | NTF | TT_NTF_150 | 2 Medium | Functional | When passing authority unpasses a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has unpassed #TicketId" |  | Amreen
153 | CT | TT_CT_153 | 2 Medium | Functional | Upon Basket creation, basket owner didnt receive notification #TT9144 |  | Amreen
154 | CT | TT_CT_154 | 1 High | Functional | Basket owner (not ticket owner) should not have access to create basket. |  | Amreen
157 | CSM | TT_CSM_157 | 2 Medium | Functional | According to "user is having less ticket" approach ticket is not assigning. it is assigned to person who is not selected in "select user" |  | Priyanka
158 | DB | TT_DB_158 | 2 Medium | Functional | task name are not displaying proper. |  | Priyanka | 17/02/2023
159 | NTF | TT_NTF_159 | 2 Medium | Functional | When there are more than one Ticket Passing Authority person, notification should be sent to all Passing Authority person, it being sent to only one person. |  | Amreen
160 | NTF | TT_NTF_160 | 2 Medium | Functional | Notification should be received to basket owner while creation of basket. |  | Amreen
161 | NTF | TT_NTF_161 | 2 Medium | Functional | When sender mentions a user in comment, Ticket owner is not getting correct notification. Test data : Ticket owner is getting Notification : "Sender has mentioned you in TicketID" |  | Amreen
162 | NTF | TT_NTF_162 | 2 Medium | Functional | Assigned to person is not receiving notification upon ticket assigning, when Assign to person assigns it to other person. |  | Amreen
163 | NTF | TT_NTF_163 | 1 High | Functional | Upon creation of ticket where selecting query as "New Implementation" , Ticket not displaying at New Implementation user login. Test data : TT9172 |  | Amreen
164 | MT | TT_MT_164 | 2 Medium | Functional | Though passing authority passed the ticket however it is not reached to Assign To person bucket |  | Priyanka
168 | NTF | TT_NTF_168 | 2 Medium | Functional | Notification displayed on Notificatios page and under notification bell icon are different. |  | Amreen
169 | NTF | TT_NTF_169 | 2 Medium | Functional | Chnages made on notification same should reflect on notification bell icon displaying different |  | Amreen
170 | PM | TT_PM_170 | 2 Medium | Functional | At project Master, Upon Edit, user field not populated |  |  | 17/02/2023
171 | PM | TT_PM_171 | 2 Medium | Functional | At project Master, Upon Edit, Description field not accepting Enter |  |  | 17/02/2023
172 | NTF | TT_NTF_172 | 2 Medium | Functional | At project Master, Upon Edit, user field not populated |  |  | 17/02/2023
173 | NTF | TT_NTF_173 | 2 Medium | Functional | Upon task creation, ticket owner not getting notification message. |  | Amreen
174 | NTF | TT_NTF_174 | 2 Medium | Functional | Upon task creation for muliple user, task owners not getting notification message. |  | Amreen
175 | NTF | TT_NTF_175 | 2 Medium | Functional | Upon task creation for mutiple user, task should be displayed all the user added under that task. Not displaying to all user. It is being displayed to only task owner. |  | Amreen
177 | NTF | TT_NTF_177 | 2 Medium | Functional | Upon clicking on to the notification it should redirect to respective page. |  | Amreen
178 | NTF | TT_NTF_178 | 2 Medium | Functional | Upon group activity creation, task owner not getting notification message. |  | Amreen
179 | NTF | TT_NTF_179 | 2 Medium | Functional | In Your notification page -> Clear all option should be added |  | Amreen
181 | PM | TT_PM_181 | 2 Medium | Functional | Project Owner not getting Ticket update related notification |  | Preeti
Project - Ticketing System, project owner - Preeti12(username)
182 | PM | TT_PM_182 | 2 Medium | Functional | Project owner won't get ticket creation notification as this field is not part of ticket create |  | Preeti
183 | NTF | TT_NTF_183 | 2 Medium | Functional | Ticket owner not getting notification for task assigned to multiple users |  | Amreen
184 | NTF | TT_NTF_184 | 2 Medium | Functional | Notification page -> all notification should dsiplay only recent 20 notifications are being displayed |  | Amreen
185 | NTF | TT_NTF_185 | 2 Medium | Functional | Notification page -> Page scroll bar not added |  | Amreen
186 | NTF | TT_NTF_186 | 2 Medium | Functional | Task completion notification not being sent to ticket owner |  | Amreen
186 | NTF | TT_NTF_186 | 2 Medium | Functional | Mulple user -> task completion notification not being sent to to all user in that task |  | Amreen
186 | NTF | TT_NTF_186 | 2 Medium | Functional | Upon task creation, ticket owner not getting proper notification message. "Task has been assigned by Amreen Shaikh for TT9161". It should display "Task has been created by Amreen Shaikh for TT9161" |  | Amreen
188 | MT | TT_MT_188 | 1 High | Functional | User won't get OTP through WhatsApp and SMS channel |  | Preeti
189 | MT | TT_MT_189 | 1 High | Functional | While edit the ticket , if user changed the status from unsolved to Reject or other than Solved status, user gets Error " Request Error" |  | Preeti | 17/02/2023
189 | NTF | TT_NTF_189 | 2 Medium | Functional | Notification is not being sent to ticket owner when any changes have been made in the Basket |  | Amreen
190 | MT | TT_MT_190 | 3 Low | Functional | For Solved Tickets, through Search Edit option is available however there is no submit button. For Solved tickets only view option should available and Comment section should not be there |  | Preeti
190 | NTF | TT_NTF_190 | 2 Medium | Functional | Notification is not being sent to ticket owner when any changes have been made in the Task |  | Amreen
191 | NTF | TT_NTF_191 | 2 Medium | Functional | Notification is not being sent to Basket owner when any changes have been made by task owner / ticket owner in the Basket |  | Amreen
192 | NTF | TT_NTF_192 | 2 Medium | Functional | Notification is not being sent to Task owner when any changes have been made by basket owner / ticket owner in the Task |  | Amreen
193 | NTF | TT_NTF_193 | 2 Medium | Functional | Notification is not being sent to ticket owner and task owner when any task been pending. |  | Amreen
194 | NTF | TT_NTF_194 | 1 High | Functional | Notification is not being sent to ticket creator after masking ticket status as SOLVED. |  | Amreen
195 | CSM | TT_CSM_195 | 1 High | Functional | Unable to edit the Customer Mapping |  | Preeti
196 | CSM | TT_CSM_196 | 1 High | Functional | System is allowing to create twice customer mapping with same Query and Department combination . How would system knows which approch needs to apply for ticket creation of specific department. |  | Preeti
Here Testing9027(Query) and IT testing(Department) with Approach - Ratio wise
Testing9027(Query) and IT testing(Department) with Approach - Having Less Ticket
197 | CSM | TT_CSM_197 | 3 High | Functional | Approach name displayed in abbreviated form. |  | Preeti
198 | CSM | TT_CSM_198 | 1 High | Functional | With Ratio Wise Customer mapping approach - Tickets are assigned to wrong person which are not included in the user list |  | Preeti
199 | CSM | TT_CSM_199 | 1 High | Functional | Systeem allowing to do customer mapping with deactive user. |  | Preeti
In user select box - along with active user deactive user also populated.
200 | CSM | TT_CSM_200 | 3 Low | Functional | Though total ratio is 100% , still it is showing error “ Total should be 100” |  | Preeti
201 | CSM | TT_CSM_201 | 3 Low | Functional | Ratio Wise - Total - displays 'Nan' instead of numerical figure. |  | Preeti
201 | MT | TT_MT_201 | 1 High | Functional | Though customer has Ticket Type show , my Tickets or Department Tickets , user can see only Created by me tab only
202 | NTF | TT_NTF_202 | 2 Medium | Functional | Buffer notifications is not being sent to task owner before the deadline to finish the task |  | Amreen
203 | NTF | TT_NTF_203 | 2 Medium | Functional | Buffer notifications is not being sent to Ticket owner before the deadline to finish the task |  | Amreen
204 | NTF | TT_NTF_204 | 2 Medium | Functional | Buffer notifications is not being sent to Basket owner before the deadline to finish the task |  | Amreen
205 | NTF | TT_NTF_205 | 2 Medium | Functional | Buffer notifications is not being sent to Ticket owner before the deadline to finish the task |  | Amreen
206 | MT | TT_MT_206 | 1 High | Functional | Upon task creation for any other user, it been observed that other user have authority to create basket and new task, for other user create basket / create task should be disabled.