## Sheet1
TT9027 - Scope Details
Module | Sub Module | Create Fields
Masters | User Master
Customer Master
Country Master
State Master
City Master
Designation Master
Department Master
Role Master
Status Master
Customer Type Master
Dynamic Form
Query Type Master
Template Master
Customer Mapping
Dynamic Form Dropdown
Ticket | My Ticket
Create Ticket

## Sheet2
[12 empty] | EFD | Remark
15 | UM | TT_UM_15 | 44953 | 1 High | 3 Low | User Master | Edit User | New | Functional | 4.WhatsApp Number : Editable and allows user to enter more than 10 digits. It is accepting all ten digits as ‘0’. Expected result - it should accept 10 digits - 1 to 9 digit and zero can be accepted at last digit. |  | 2023-02-13
29 | UM | TT_UM_29 | 44956 | 2 Medium | 3 Low | User Master | Edit User | reopen | Functional | While trying to change the department at edit user screen , system is not allowing . ( No action reaction seen after click on submit button) |  | 14/2/2023
1. select user for Edit
2. change the department
3. click on Submit button
61 | MT | TT_MT_61 | 44959 | 1 High | 1 High | Ticket | Basket | reopen | Functional | When basket owner have access to play and pause the task of assigned users then when it is group task he is not able to play and pause the same task. | Priyanka |  |  | Rushikesh | 44965 | Sheet3!A95
62 | MT | TT_MT_62 | 44959 | 1 High | 1 High | Ticket | Basket | reopen | Functional | 5. When basket owner has created task for 3 people and he is not part of that task still he can play the and pause the task. It is expected that he should not be having authority to play the task or group activity of another user. He should be able to review task timings. | Priyanka |  |  | Rushikesh | 44965 | Sheet3!A120
75 | MTB | TT_MTB_75 | 44960 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | reopen | Functional | While creating basket start date field is accepting greater date than end date. Need validation to start date and end date. | Priyanka | 14/02/2023 |  |  | 44965
76 | MTB | TT_MTB_76 | 44960 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | reopen | Functional | Basket Name, select user, start date and end date are mandatory fields are not having mandatory star mark. | Priyanka | 14/02/2023 |  |  | 44965
77 | MTB | TT_MTB_77 | 44960 | 2 Medium | 2 Medium | Ticket | My Ticket -Basket | reopen | Functional | Added baskets are not arranged properly | Priyanka |  |  | Rushikesh | 44965
[10 empty] | When screens size gets reduces basket alignment not arranged properlysqueeze |  |  |  | Rushikesh
78 | MTT | TT_MTT_78 | 44960 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | reopen | Functional | While creating task end date picker should not be accept smaller date than start date. | Priyanka | 14/02/2023 |  |  | 44965
82 | MTT | TT_MTT_82 | 44960 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | New | Functional |  | Priyanka
90 | MTT | TT_MTT_90 | 44963 | 2 Medium | 2 Medium | Ticket | My Ticket -Task | reopen | Functional | “from” and “to date” field need validation. To date field accepts smaller date than from date. | Priyanka | 14/02/2023 |  |  | 44965
94 | UTR | TT_UTR_94 | 44963 | 2 Medium | 2 Medium | Ticket | export | reopen | Functional | filtered record doesn’t export all data is exported in file. | Priyanka | 14/02/2023 |  |  | 44965
108 | UM | TT_UM_108 | 44964 | 3 Low | 3 Low | Master | User master - Edit User | New | Functional | Contact number Validation is not applied for WhatsApp Number . Contact number validation should reflect for WhatsApp Number | Preeti | 14/02/2023
111 | UM | TT_UM_111 | 44964 | 2 Medium | 2 Medium | Masters | All master - Address | New | Functional | Address Field is not accepting " Enter" key( new line). it should accept. | Preeti | 14/02/2023
113 | CT | TT_CT_113 | 44964 | 2 Medium | 2 Medium | Ticket | Create Ticket - Bulk Uploading | New | Functional | For Bulk uploading though default department populated , still system throws error " please select department and Query Type" . User has to select the value from dropdown inspite of one or many department. | Preeti |  |  | Rushikesh
114 | CT | TT_CT_114 | 44965 | 3 Low | 3 Low | Ticket | Create Ticket - Bulk Uploading | New | Functional | For Bulk upload, user has to click 1st on 'Generate Bulk Format' and then click on 'Download file' then only user can proceed for Bulk uploading. | Preeti |  |  | Rushikesh
[10 empty] | Can we omit the 'Generate Bulk format' click on step. |  |  |  | Rushikesh
116 | VR | TT_VR_116 | 44964 | 2 Medium | 2 Medium | Reports | export | New | Functional | "Complted at" column is not present in variance report grid still it is displayed in downloaded file. |  |  |  | Rushikesh
117 | RP | TT_RP_117 | 44965 | 2 Medium | 1 High | Reports | Resource planning | New | Functional | while selecting user in "select user" dropdown it redirects to blank page. | Priyanka | 15/02/2023
121 | RP | TT_RP_121 | 44965 | 2 Medium | 1 High | reports | Resource planning | new | functional | when we selects user in "select user" field and clicked on search it doesnt display report. | priyanka | 15/02/2023
122 | RP | TT_RP_122 | 44965 | 2 Medium | 2 Medium | reports | resource planning | new | functional | "from date", and "to date" fields are mandatory it is not having mandatory star mark. and if user left any field empty it doesnt display error warning message. | priyanka | 15/02/2023
123 | MT | TT_MT_123 | 44965 | 2 Medium | 2 Medium | Ticket | Manage task | new | functional | when we edit task it doesnt load proper "Assign to user" and dependent task field. | priyanka | 15/02/2023 |  |  |  | Sheet3!A15
124 | RP | TT_RP_124 | 44965 | 2 Medium | 2 Medium | reports | resource planning | new | functional | user names should be dislay in ascending order in "Select user" dropdown. | priyanka | 16/02/2023
125 | RP | TT_RP_125 | 44965 | 2 Medium | 2 Medium | reports | resource planning | new | functional | without selecting "select user" if filter the records according to date user names are not displayed in proper order. | priyanka | 16/02/2023
126 | MT | TT_MT_126 | 44965 | 2 Medium | 2 Medium | Ticket | Manage Task | new | functional | not working proper while play pause the group activity. | priyanka |  |  | Rushikesh
127 | MT | TT_MT_127 | 44965 | 2 Medium | 2 Medium | Ticket | Manage task | new | functional | when it is "group tasks" or "group activity" it is not arrranged properly. | priyanka |  |  | Rushikesh |  | Sheet3!A42
128 | MT | TT_MT_128 | 44965 | 2 Medium | 2 Medium | Ticket | Manage task | new | functional | when user have multiple baskets at a time different "group activities" are playing from "differnet baskets" of same user. | priyanka |  |  | Rushikesh |  | Sheet3!A71
129 | MT | TT_MT_129 | 44965 | 2 Medium | 2 Medium | Ticket | Manage task | new | functional | When user has created task and after it is edited with "group activity" play pause functionality is not working properly. | priyanka |  |  | Rushikesh
130 | MT | TT_MT_130 | 44965 | 2 Medium | 2 Medium | Ticket | Manage task | new | functional | when "basket owner" is not part of specific task he should not be having authority to send the regularization request. | priyanka |  |  | Rushikesh
133 | CB | TT_CB_133 | 44965 | 3 Low | 3 Low | Ticket | View - Chatbot | New | UI | Send button location is different from Edit view. | Priyanka | 16/02/2023
134 | CB | TT_CB_134 | 44965 | 2 Medium | 2 Medium | Ticket | Edit View - Chatbot | New | Functional | Mention text displays Twice | Preeti |  |  | Rushikesh
135 | CB | TT_CB_135 | 44965 | 3 Low | 3 Low | Ticket | Edit View - Chatbot | New | Functional | Text is displayed in blue colour, expected to display in black colour | Preeti |  |  | Rushikesh
136 | MT | TT_MT_136 | 44966 | 0 Blocker | 1 High | Ticket | Create Ticket | New | Functional | While creating the ticket it has ben observed that Ticket assigned to deactive user and further journey is not progressing. | Amreen |  |  | Rushikesh
140 | MT | TT_MT_140 | 44966 | 2 Medium | 1 High | Manage task | Task planner | New | Functional | "planner" option should not be visible for completed tasks. | Priyanka | 17/02/2023 |  | Rushikesh |  | Sheet3!A147
141 | MT | TT_MT_141 | 44966 | 2 Medium | 2 Medium | Manage task | Task planner | New | Functional | user can enter the back date in planner."date" field should be disable. | Priyanka | 16/02/2023
142 | MT | TT_MT_142 | 44966 | 1 High | 2 Medium | Manage task | Task planner | New | Functional | If in planner "divided task hours" and "scheduled task hours" are not equal still task is getting updated. it doesnt display warning message. | Priyanka | 17/02/2023
143 | MT | TT_MT_143 | 44966 | 2 Medium | 2 Medium | Manage task | Task planner | New | Functional | If it is group task and I have edited "Assigned user" and assigned same user in planner it doesnt display any error message. | Priyanka | 17/02/2023
144 | CSM | TT_CSM_144 | 44966 | 2 Medium | 2 Medium | masters | Edit customer mapping | New | Functional | previously selected users are not displaying in edit customer mapping. | priyanka |  |  | Rushikesh
145 | CSM | TT_CSM_145 | 44966 | 2 Medium | 2 Medium | masters | Edit customer mapping | New | Functional | Department wise usernames are not displaying in "select user" field. | priyanka |  |  | Rushikesh
146 | CSM | TT_CSM_146 | 44966 | 2 Medium | 2 Medium | masters | Edit customer mapping | New | Functional | User is not able to update users in "select user" field. | priyanka |  |  | Rushikesh
147 | CSM | TT_CSM_147 | 44966 | 2 Medium | 2 Medium | masters | create customer mapping | New | Functional | while creating customer mapping even though mapping is not done it displays successful message"Record inserted." | priyanka |  |  | Rushikesh
148 | CT | TT_CT_148 | 44966 | 2 Medium | 2 Medium | Ticket | Create Ticket | New | Functional | Passing Authority should receive notification if any user of the same department creates ticket the and that ticket should come under his unpassed ticket list. | Amreen |  |  | Rushikesh
149 | NTF | TT_NTF_149 | 44966 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | When passing authority passes a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has passed #TicketId" | Amreen |  |  | Rushikesh
150 | NTF | TT_NTF_150 | 44966 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | When passing authority unpasses a ticket, ticket creator should rcv notification stating "#PassingAuthorityName has unpassed #TicketId" | Amreen |  |  | Rushikesh
153 | CT | TT_CT_153 | 44966 | 2 Medium | 2 Medium | Ticket | Create Ticket | New | Functional | Upon Basket creation, basket owner didnt receive notification #TT9144 | Amreen |  |  | Rushikesh
154 | CT | TT_CT_154 | 44966 | 1 High | 1 High | Ticket | Create basket | New | Functional | Basket owner (not ticket owner) should not have access to create basket. | Amreen |  |  | Rushikesh
157 | CSM | TT_CSM_157 | 44966 | 2 Medium | 2 Medium | masters | create customer mapping | New | Functional | According to "user is having less ticket" approach ticket is not assigning. it is assigned to person who is not selected in "select user" | Priyanka |  |  | Rushikesh
158 | DB | TT_DB_158 | 44966 | 2 Medium | 2 Medium | dashboard | My tasks | New | Functional | task name are not displaying proper. | Priyanka | 17/02/2023
159 | NTF | TT_NTF_159 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | When there are more than one Ticket Passing Authority person, notification should be sent to all Passing Authority person, it being sent to only one person. | Amreen |  |  | Rushikesh
160 | NTF | TT_NTF_160 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification should be received to basket owner while creation of basket. | Amreen |  |  | Rushikesh
161 | NTF | TT_NTF_161 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | When sender mentions a user in comment, Ticket owner is not getting correct notification. Test data : Ticket owner is getting Notification : "Sender has mentioned you in TicketID" | Amreen |  |  | Rushikesh
162 | NTF | TT_NTF_162 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Assigned to person is not receiving notification upon ticket assigning, when Assign to person assigns it to other person. | Amreen |  |  | Rushikesh
163 | NTF | TT_NTF_163 | 44967 | 1 High | 1 High | Ticket | Notification | New | Functional | Upon creation of ticket where selecting query as "New Implementation" , Ticket not displaying at New Implementation user login. Test data : TT9172 | Amreen |  |  | Rushikesh
164 | MT | TT_MT_164 | 44967 | 2 Medium | 2 Medium | Tickets | My tickets | New | Functional | Though passing authority passed the ticket however it is not reached to Assign To person bucket | Priyanka |  |  | Rushikesh
168 | NTF | TT_NTF_168 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification displayed on Notificatios page and under notification bell icon are different. | Amreen |  |  | Rushikesh
169 | NTF | TT_NTF_169 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Chnages made on notification same should reflect on notification bell icon displaying different | Amreen |  |  | Rushikesh
170 | PM | TT_PM_170 | 44967 | 2 Medium | 2 Medium | Project master | Edit Project | New | Functional | At project Master, Upon Edit, user field not populated |  | 17/02/2023 | resolved15/02/2023
171 | PM | TT_PM_171 | 44967 | 2 Medium | 2 Medium | Project master | Edit Project | New | Functional | At project Master, Upon Edit, Description field not accepting Enter |  | 17/02/2023 | resolved15/02/2023
172 | NTF | TT_NTF_172 | 44967 | 2 Medium | 2 Medium | Project master | Edit Project | New | Functional | At project Master, Upon Edit, user field not populated |  | 17/02/2023 | resolved15/02/2023
173 | NTF | TT_NTF_173 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon task creation, ticket owner not getting notification message. | Amreen |  |  | Rushikesh
174 | NTF | TT_NTF_174 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon task creation for muliple user, task owners not getting notification message. | Amreen |  |  | Rushikesh
175 | NTF | TT_NTF_175 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon task creation for mutiple user, task should be displayed all the user added under that task. Not displaying to all user. It is being displayed to only task owner. | Amreen |  |  | Rushikesh
177 | NTF | TT_NTF_177 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon clicking on to the notification it should redirect to respective page. | Amreen |  |  | Rushikesh
178 | NTF | TT_NTF_178 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon group activity creation, task owner not getting notification message. | Amreen |  |  | Rushikesh
179 | NTF | TT_NTF_179 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | In Your notification page -> Clear all option should be added | Amreen |  |  | Rushikesh
181 | PM | TT_PM_181 | 44967 | 1 High | 2 Medium | Ticket | Notification | New | Functional | Project Owner not getting Ticket update related notification | Preeti |  |  | Rushikesh
[10 empty] | Project - Ticketing System, project owner - Preeti12(username) |  |  |  | Rushikesh
182 | PM | TT_PM_182 | 44967 | 1 High | 2 Medium | Ticket | Notification | New | Functional | Project owner won't get ticket creation notification as this field is not part of ticket create | Preeti |  |  | Rushikesh
183 | NTF | TT_NTF_183 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Ticket owner not getting notification for task assigned to multiple users | Amreen |  |  | Rushikesh
184 | NTF | TT_NTF_184 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification page -> all notification should dsiplay only recent 20 notifications are being displayed | Amreen |  |  | Rushikesh
185 | NTF | TT_NTF_185 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification page -> Page scroll bar not added | Amreen |  |  | Rushikesh
186 | NTF | TT_NTF_186 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Task completion notification not being sent to ticket owner | Amreen |  |  | Rushikesh
186 | NTF | TT_NTF_186 | 44967 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Mulple user -> task completion notification not being sent to to all user in that task | Amreen |  |  | Rushikesh
186 | NTF | TT_NTF_186 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Upon task creation, ticket owner not getting proper notification message. "Task has been assigned by Amreen Shaikh for TT9161". It should display "Task has been created by Amreen Shaikh for TT9161" | Amreen |  |  | Rushikesh
188 | MT | TT_MT_188 | 44967 | 1 High | 1 High | Ticket | Edit Ticket | New | Functional | User won't get OTP through WhatsApp and SMS channel | Preeti |  |  | Rushikesh
189 | MT | TT_MT_189 | 44967 | 1 High | 1 High | Ticket | Edit Ticket | New | Functional | While edit the ticket , if user changed the status from unsolved to Reject or other than Solved status, user gets Error " Request Error" | Preeti | 17/02/2023
189 | NTF | TT_NTF_189 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification is not being sent to ticket owner when any changes have been made in the Basket | Amreen |  |  | Rushikesh
190 | MT | TT_MT_190 | 44967 | 3 Low | 3 Low | Ticket | Edit Ticket | New | Functional | For Solved Tickets, through Search Edit option is available however there is no submit button. For Solved tickets only view option should available and Comment section should not be there | Preeti |  |  | Rushikesh
190 | NTF | TT_NTF_190 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification is not being sent to ticket owner when any changes have been made in the Task | Amreen |  |  | Rushikesh
191 | NTF | TT_NTF_191 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification is not being sent to Basket owner when any changes have been made by task owner / ticket owner in the Basket | Amreen |  |  | Rushikesh
192 | NTF | TT_NTF_192 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification is not being sent to Task owner when any changes have been made by basket owner / ticket owner in the Task | Amreen |  |  | Rushikesh
193 | NTF | TT_NTF_193 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Notification is not being sent to ticket owner and task owner when any task been pending. | Amreen |  |  | Rushikesh
194 | NTF | TT_NTF_194 | 44968 | 1 High | 1 High | Ticket | Notification | New | Functional | Notification is not being sent to ticket creator after masking ticket status as SOLVED. | Amreen |  |  | Rushikesh
195 | CSM | TT_CSM_195 | 44968 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | New | Functional | Unable to edit the Customer Mapping | Preeti |  |  | Rushikesh
196 | CSM | TT_CSM_196 | 44968 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | New | Functional | System is allowing to create twice customer mapping with same Query and Department combination . How would system knows which approch needs to apply for ticket creation of specific department. | Preeti |  |  | Rushikesh
Here Testing9027(Query) and IT testing(Department) with Approach - Ratio wise
Testing9027(Query) and IT testing(Department) with Approach - Having Less Ticket
197 | CSM | TT_CSM_197 | 44968 | 3 High | 3 High | Customer Mapping | Grid View | New | Functional | Approach name displayed in abbreviated form. | Preeti |  |  | Rushikesh
198 | CSM | TT_CSM_198 | 44968 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | New | Functional | With Ratio Wise Customer mapping approach - Tickets are assigned to wrong person which are not included in the user list | Preeti |  |  | Rushikesh
199 | CSM | TT_CSM_199 | 44968 | 1 High | 1 High | Customer Mapping | Create Customer Mapping | New | Functional | Systeem allowing to do customer mapping with deactive user. | Preeti |  |  | Rushikesh
In user select box - along with active user deactive user also populated.
200 | CSM | TT_CSM_200 | 44968 | 0 Low | 3 Low | Customer Mapping | Create Customer Mapping | New | Functional | Though total ratio is 100% , still it is showing error “ Total should be 100” | Preeti |  |  | Rushikesh
201 | CSM | TT_CSM_201 | 44968 | 0 Low | 3 Low | Customer Mapping | Create Customer Mapping | New | Functional | Ratio Wise - Total - displays 'Nan' instead of numerical figure. | Preeti |  |  | Rushikesh
201 | MT | TT_MT_201 | 44968 | 1 High | 1 High | My Ticket | Created by me or Department wise | New | Functional | Though customer has Ticket Type show , my Tickets or Department Tickets , user can see only Created by me tab only |  |  |  | backend issue
202 | NTF | TT_NTF_202 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Buffer notifications is not being sent to task owner before the deadline to finish the task | Amreen |  |  | Rushikesh
203 | NTF | TT_NTF_203 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Buffer notifications is not being sent to Ticket owner before the deadline to finish the task | Amreen |  |  | Rushikesh
204 | NTF | TT_NTF_204 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Buffer notifications is not being sent to Basket owner before the deadline to finish the task | Amreen |  |  | Rushikesh
205 | NTF | TT_NTF_205 | 44968 | 2 Medium | 2 Medium | Ticket | Notification | New | Functional | Buffer notifications is not being sent to Ticket owner before the deadline to finish the task | Amreen |  |  | Rushikesh
206 | MT | TT_MT_206 | 44970 | 1 High | 1 High | My Task |  | New | Functional | Upon task creation for any other user, it been observed that other user have authority to create basket and new task, for other user create basket / create task should be disabled. |  |  |  | Rushikesh