## Issue Tracking Template
Issue Tracking Template- TT3711 Tech ticket Mobile App Phase 1
ID | Description | Potential Impact | Priority | Date Opened | Date Closed | Issue Owner | Solution Department | Status | Notes
1 | Play task, then close the app. When we click on pause button through notification, then it is not pausing the task instaed it is directing user to dashboard page. Whereas, task remains in played state. | 80% - User might be in consideration that his task has got paused just by clicking on pause from notification button itself. | High | 2023-08-09 |  | Manali Bhadirage | Flutter Dev - GB | Open | It will take 6 working days time to research and develop.
2 | When we play any task and mark that task as complete from web, then in notification the task is getting as played and it shows message as 'something went wrong' until we refresh the dashboard page. | 50% - Socket issue. Time for completed task get stopped even if is showing in notification list until we refresh. But due to this user will consider that their task is still in played state even after marking it as complete. | Medium | 2023-08-12 |  | Manali Bhadirage | Flutter Dev - GB | Open | When there are not tasks in today's list then it is showing message as 'something went wrong'. This should be resolved.
3 | If we login and play task, it appears in notification list. Then further when we close the app, click on notification then it directs user to dashboard page but then notification disappears even if task is in played state. To make notification appear, we have to play and pause some task again. | 30% - This is increasing actions for users. | Medium | 2023-08-11 |  | Manali Bhadirage | Flutter Dev - GB | Open | It will take 4 working days to resolve this.
4 | When we visit app each time, it takes time to load tasks on dashboard and is displaying 'something went wrong' message even if there is no issue. | 10% - | Low | 2023-08-12 |  | Manali Bhadirage | Flutter Dev - GB | Open | When there are not tasks in today's list then it is showing message as 'something went wrong'. This should be resolved. 2 hours for loading issue.
5 | Searched tasks is not getting highlighted | 50% - This functionality was working on dummy apk once. | Medium | 2023-08-09 | 2023-08-11 | Manali Bhadirage | Flutter Dev - GB | Closed | Closed
6 | If we play random task from middle of the list, it appears in notification list. When we pause that task from notification list. It displays that played task as serial number 1. However when we play that task, then first task of the list gets played and not the one which we paused. | 80% - User might be in consideration that he is playing the ptask that he has paused. But in actual list if getting refreshed on pausing tasks and then it is playing the first task of that list. | High | 2023-08-09 | 2023-08-11 | Manali Bhadirage | Flutter Dev - GB | Closed | It takes few seconds to load the list in notification playlist and then first task for the list gets displayed. 1 hour required.
7 | Remember me button is only saving and prefilling recently saved credentials. It is not saving and prefilling all saved credentials. | 5% - | Low | 2023-08-09 |  | Manali Bhadirage | Flutter Dev - GB | Closed | It shopuld save all passwords and display the list when user clicks on username field. Only one password saving should be allowed as informed by Gaurav sir on 18/08/2023 at 7:30pm.
8 | Sometimes getting issue to refresh dashboard page | 30% - | Medium | 2023-08-18 |  | Manali Bhadirage | Flutter Dev - GB | Open | 1 hour required.
9
10
11
12

## 5W1H
What? | Why? | When? | Who? | which? | How?
What is hypercare? - the service of providing intense system support between the time of go live and project closure. | why is it needed? - For stabilization of product after go-live | After a software launch and before project closure | Developer, tester, BA, PM, SMEs, stakeholders (customers) | which methodolgy? - In Waterfall. For many teams who makes the switch from Waterfall to Agile, management still demand the need of hypercare process. In agile methodology, gaps are recorded in the backlog. The backlog items may be selected for the next sprint. Thus hypercare is same as sprint in agile. | How is this helpful? To understand reported issue is missed bug / change request / suggestion / reopened bug. To know observed issues were already reported during testing or not or got ignored. Ensure that progress is appropriately reported, controlled and maintained.
what does it include? - understand how to use the new product / service / feature. | To ensure a smooth transition and address any issues that may arise during the initial phase of implementation. |  |  |  | For how much period? - Two days / two - four weeks depending on project
What is difference between hypercare and support? - Hypercare is special attention and work immediately after a launch for final closure. Support is continued project support after launch.