## SimpleTaskTracker
E-GOLD PROJECT TRACKER
STAGE | DELIVERABLES | PRIORITY | START DATE | END DATE | EST HOURS | % COMPLETE | DONE | OWNER | NOTES
Requirement gathering and analysis | Requirement gathering | 4 |  |  |  | 100% | 1
Documentation and updates | Mobile App Documentation (phase 1 and phase 2) | 4 | 16/05/2023 | 26/05/2023 |  | 95% | 1
UI UX | UI UX Design (all screens) | 3 | 2021-01-02 | 27/06/2023 |  | 95% | 1
Documentation and updates | Web app documentation (phase 1) | 4 | 27/06/2023 | 29/06/2023 |  |  | 0
Database structure and table designing | Setup and UI Design development (23 screens) | 3 | 27/06/2023 | 28/06/2023 |  |  | 0 | DC
Database structure and table designing | Setup | 4 | 27/06/2023 | 27/03/2023 |  |  | 0
Database structure and table designing | Database structure design |  | 27/06/2023 | 27/03/2023 |  |  | 0 | NB
Database structure and table designing | Database table creation |  | 27/06/2023 | 27/06/2023 |  |  | 0 | PS
Development | API development (30+) |  | 28/06/2023 | 28/06/2023 |  |  | 0 | PS
Testing | API testing |  | 28/06/2023 | 29/06/2023 |  |  | 0 | PB, PD
Testing | End to end Test cases writing (app) |  | 27/06/2023 | 27/06/2023 |  |  | 0 | PB, PD
Testing | End to end Test cases writing (web) |  | 28/06/2023 | 28/06/2023 |  |  | 0 | PB, PD
Testing | UI testing |  | 29/06/2023 | 29/06/2023 |  |  | 0 | PD, PB
Development | Registration, logi, forgot password api integration + development |  | 28/06/2023 | 28/06/2023 |  |  | 0 | DC
Testing | Registration, login, forgot password, sign out testing |  | 29/06/2023 | 29/06/2023 |  |  | 0 | PB
Development | buy, rate trigger api integration + development |  | 29/06/2023 | 29/06/2023 |  |  | 0 | DC
Development | Dashboard, payment integration, create SIP, Sell api integration + development |  | 29/06/2023 | 29/06/2023 |  |  | 0 | GB
Development | forget password development |  | 28/06/2023 | 28/06/2023 |  |  | 0 | DC |  | payment gateway 29/06/2023
Development | delivery, nominee, notification api integration + development |  | 29/06/2023 | 29/06/2023 |  |  | 0 | GB
Testing | buy, sell testing |  | 30/06/2023 | 30/06/2023 |  |  | 0 | PB
Development | your trades, profile api integration and development |  | 30/06/2023 | 30/06/2023 |  |  | 0 | DC
Testing | SIP testing |  | 30/06/2023 | 30/06/2023 |  |  | 0 | PD
Development | manage SIP |  | 30/06/2023 | 30/06/2023 |  |  | 0 | GB
0
0

## Test case scenarios
SR NO. | FUNCTIONALITY | SCENARIO | NAME
1 | Notification | To verify that customer receives welcome notification within app after registering and logging in for the first time. | MB
2 |  | To verify that customer receives notification within app after updating any field in profile. | MB
3 |  | To verify that cx receives notification within app as well as on another medium as set after succesful buy transaction. | MB
4 |  | To verify that cx receives notification within app as well as on another medium as set after succesful sell transaction. | MB
5 |  | To verify that cx receives notification within app as well as on another medium as set after succesful SIP transaction of each month. | MB
6 |  | To verify that cx receives notification within app for unsuccesful buy transaction. | MB
7 |  | To verify that cx receives notification within app for unsuccesful sell transaction. | MB
8 |  | To verify that cx receives notification within app for unsuccesful SIP transaction for each month. | MB
9 |  | To verify that cx receives notification within app as well as on another medium as set after succesful delivery transaction. | MB
10 |  | To verify that cx receives notification within app for unsuccesful delivery transaction. | MB
11 |  | To verify that cx receives notification within app after adding bank details. | MB
12 |  | To verify that cx receives notification within app after updating bank details. | MB
13 |  | To verify that cx receives notification within app after adding nominee details. | MB
14 |  | To verify that cx receives notification within app after updating nominee details. | MB
15 |  | To verify that cx receives notifivcation within app as well as on another medium as set when delivery is marked as delivered by tenant through web. | MB
16 |  | To verify that cx received notification about set rate trigger within app as well as on medium which is set. | MB
17 |  | To verify that cx receives notification only within app and not on any another medium until preferece settings are set. | MB
18 |  | To verify that cx receives notifcation within application as sent by tenant | MB
19 |  | To verify that cx receives SIP reminder notifcation 5 days prior to their upcoming SIP date | MB
20 |  | To verify that recently received notification is displayed at top with date and time on notification menu | MB
21 |  | To verify that cx receives notification within app and on medium set when rate trigger is cancelled. | MB
22 |  | To verify that cx doesn't receive notification on another mediums once user un-check through preference settings. | MB
1 | Your Trades | To verify that transaction of succesful buy is displayed in your trades | MB
2 |  | To verify that transaction of succesful sell is displayed in your trades | MB
3 |  | To verify that transaction of succesful monthly SIP is displayed in your trades. | MB
4 |  | To verify that transaction of succesful delivery is displayed in your trades | MB
5 |  | To verify that updated weight balance of gold / silver is displayed in your trades after any successful transaction. | MB
6 |  | To verify that all details of each transaction are displayed correctly in your trades first view as well as in receipt. | MB
7 |  | To verify that cx is able to share his trade receipt via whatsapp / any other medium. | MB
8 |  | To verify that cx is able to email his invoice of each trade | MB
9 |  | To verify that cx can download receipt of each trade in his device. | MB
10 |  | To verify that cx can view all correct trade details after filtering by date and trade type. | MB
11 |  | To verify that cx can export excel file about all trades done till now by customer. | MB
12 |  | To verify that 100 trades done till the current date are being displayed in page wise manner of your trades. | MB
1 | Delivery | To verify that total weight balance gold / silver is displayed in delivery menu. | MB
2 |  | To verify that cx is able to apply for both gold and silver delivery option. | MB
3 |  | To verify that cx is able to apply for delivery only out of total weight balance in his account. | MB
4 |  | Verify that cx is able to fill all details in delivery form | MB
5 |  | verify that delivery charges are being applied to cx as per tenant's configurable settings. | MB
6 |  | verify that all details of delivery are being displayed in billing information | MB
7 |  | verify that cx should be able to add bank details / payment gateway is displayed for proceeding after billing information | MB
8 |  | verify that notification is sent to cx within app & other medium about successful transaction | MB
9 |  | verify that cx receives notification within app about failed transaction | MB
10 |  | verify that delivery transaction and its details gets displayed in your trades | MB
11 |  | verify that weight balance gets updated and displayed after succesful delivery transaction | MB
12 |  | verify that weight balance doesn't get updated / displayed for unsuccesful delivery transaction | MB
1 | Settings -> Nominee | verify that customer is able to add details of only one nominee | MB
2 |  | Verify that added nominee details are displayed correctly | MB
3 |  | verify that cx is able to update nominee deails which were already added | MB
4 |  | verify that added nominee details are being displayed on web against cx | MB
5 | settings -> preferences | verify that settings are off / displayed blank initially until cx hasn't set any | MB
6 |  | verify that cx is able to set communication preference in sequence | MB
7 |  | verify that cx is able to enter preferred call timing | MB
8 |  | verify that cx is able to check or uncheck one or many notification mediums | MB
9 |  | verify that cx receives notifications on mediums as per settings | MB
10 |  | verify that cx is able to set pin or scan finger as biometric settings | MB
11 |  | verify that cx is asked to enter pin / scan finger when cx visits /opens the app everytime | MB
12 |  | verify that customer's settings are being displayed to tenant as set | MB
13 | settings -> bank | verify that cx is able to add different & multiple bank details | MB
14 |  | verify that added banks details are displayed correctly | MB
15 |  | verify that cx is able edit bank details only if that bank isn't used for any SIP | MB
16 |  | verify that cx is able to remove added bank from the list | MB
17 |  | verify that added bank details are displayed in the list of bank in buy / sell / SIP / delivery payment gateway | MB
18 |  | verify that removed banks are not displayed in the list of bank in buy / sell / SIP / delivery payment gateway | MB
19 |  | verify that payment transactions are done from selected bank only while buy / sell / delivery / sip | MB
20 |  | verify that for transactions are displayed correctly with correct bank details in your trades | MB
21 |  | verify that amount doesn't get deducted from bank for unsuccesful transaction | MB
1 | User Registration | Verify user with 18 age or above is able to register. | PB
2 |  | Verify user name match with Adhar, and PAN card details | PB
3 |  | Verify with one Adhar card and Pan card only one user can registered | PB
4 |  | Verify system should not allow to re - register again to already registered user, system should throw error message as ' User already registered | PB
5 |  | Verify another user is not registed with already used Aadhar card and Pan card | PB
6 |  | Verify only register user can login with OTP | PB
7 |  | Verify with valid aadhar and valid PAN number user is able to registered himself | PB
8 |  | (only register user + mobile no + aadhar card + pan card ) Unique combination | PB
9 |  | One registered user is mapped with one mobile number | PB
10 |  | Verify one tenant customer can't able to login with another tenant app | PB
1 | Sign In | Verify system should not allow unregistered user to log in to system | PB
2 |  | Verify system should not allow to unregistered user to log in with mobile number | PB
1 | Forgot Password | Verify only registered users can reset the password by providing the OTP received at registered email id | PB
2 |  | Verify system should not accept new password as old password. | PB
3 |  | Verify password length is 8 to 10 character. It must be alphanumeric +special character combination | PB
4 |  | Verify with expired OTP System should not allow to reset the password | PB
5 |  | Verify system should not allow to reset the password by another user OTP | PB
6 |  | Verify system should not allow to reset the password by already used OTP | PB
1 | Help Desk | Verify upon submitting the query , user should get unique Token id . | PB
2 |  | Against Token ID at web app as soon as Query submitted status would be reflected as Pending . | PB
3 |  | Upon query resolution , Status at web app, would change to solved | PB
4 |  | Upon click on call icon , the helpdesk no get copied to dial pad | PB
1 | SIP | Verify SIP request should not triggered twice in a month | PB
2 |  | Verify in case of short fall of SIP amount at User account , SIP status would be reflect as unsuccessful and notification should sent to user | PB
3 |  | Verify system should not allow to cancel the SIP at SIP deduction date | PB
4 |  | Verify SIP amount deducted @ SIP set monthly date and its status should match with bank response , Web app & Mobile app | PB
1 | Sell | Verify upon sell if amount is not credited to account , the amount retriggered to account | PB
2 |  | Verify if sell transaction fails at App end , Balance weight should not affect | PB
3 |  | Verify if sell transaction fails at payment gateway end , Balance weight should not affect | PB
4 |  | Verify for unsuccessful transaction Weight Balance should not affect | PB
5 |  | Verify that without KYC customer is unable to perform sell transaction. | PB
1 | Real time gold/silver rate | Verify that the rates are automatically refreshed regularly to reflect the current rate. | PD
2 |  | To verify that the displayed rates match the current market rates. | PD
3 |  | To check what if varying network connectivity, such as a stable network connection, slow connectivity. | PD
4 |  | To verify when disable the mobile device's internet connection. | PD
5 |  | Verify that the app continues to fetch and update the gold rates in real-time, even when the user switches to other apps or locks the device. | PD
6 |  | To check app's response time in fetching and displaying live gold/silver rates. | PD
7 |  | Verify that the app handles different network conditions gracefully and displays appropriate messages or indicators to inform users about the status of the connection. | PD
8 |  | verify when app rapidly switch into screens and different sections. | PD
1 | Buy | Verify user is able to purchase gold by entering amount in "Rupees" | PD
2 |  | Verify user is able to purchase gold by entering quantity in "grams". | PD
3 |  | verify system calculates correct quantity of gold when user enters amount and system calculates correct amount in rupees when user enters quantity in grams. | PD
4 |  | Without kyc of user system should not allow to buy gold/silver. | PD
5 |  | while making payment, if transaction fails user's amount should not deduct and user should get notify for same. | PD
6 |  | verify after transaction successful transaction details should reflect in your trades. | PD
7 |  | To verify after transaction successful notification is sent to user or nnot. | PD
8 |  | To check with different gold rates to ensure that the system calculates the amount correctly. | PD
9 |  | To check by entering an invalid quantity in grams, such as a negative value Ensure that the system detects the invalid input and displays an appropriate error message. | PD
10 |  | Verify user is able to purchase silver by entering amount in "Rupees" | PD
11 |  | Verify user is able to purchase silver by entering quantity in "grams". | PD
12 |  | verify system calculates correct quantity of silver when user enters amount and system calculates correct amount in rupees when user enters quantity in grams. | PD
13 |  | To check with different silver rates to ensure that the system calculates the amount correctly. | PD
14 |  | To verify if user has logged in with different two devices and performs operations simultaneously to ensure system displays the appropriate alert. | PD
1 | Offer code | To verify where a user applies a valid offer code during the gold purchase. | PD
2 |  | Verify that the system recognizes the code, applies the corresponding discount and recalculates the total amount accurately. | PD
3 |  | To verify if invalid offer code is entered by user, system should display appropriate error message. | PD
4 |  | To verify the accuracy of discount calculations when an offer code is applied. discount should get deducted from total amount of bill and then final amount should be displayed for customer. | PD
5 |  | To verify where a user applies multiple offers or discount codes simultaneously. verify that the system handles such combinations correctly. | PD
6 |  | Verify that the system prevents users from applying the offer code once the redemption limit has been reached.User can apply only one offercode for single transaction. | PD
7 |  | To check what if network failures or interruptions during the code application process.Verify that the system handles such error and displaying appropriate error messages and providing options to retry or enter a valid offer code. | PD
1 | Payment | To verify displaying a list of available banks for payment integration in the mobile app. | PD
2 |  | If user has added the new bank to verify while payment added bank lists are displaying. | PD
3 |  | Verify that the app accurately presents a list of banks that users can choose from during the payment process. | PD
4 |  | To verify initially user has not added any bank details, user should get redirected to "Add bank details" screen. | PD
5 |  | To check if user selects a bank from the list for making the payment. then verify that the app captures and stores the selected bank information correctly for further processing. | PD
6 |  | To check the integration between the app and the selected payment gateway or bank's payment system. | PD
7 |  | Verify that the app securely transfers the user to the bank's authentication page or prompts the user to enter their banking credentials. | PD
8 |  | To verify authorization process after the user authenticates their payment credentials. Ensure that the app successfully obtains the necessary authorization from the bank to proceed with the payment transaction. | PD
9 |  | To check payment confirmation message or receipt after a successful transaction. | PD
10 |  | To check during the payment process, such as bank's system is temporarily unavailable, To ensure that the app handles these situations gracefully, displaying meaningful error messages. | PD
11 |  | During the payment process if phone is restarted or switched off ensure that user have to buy procedure from beginning. | PD
12 |  | During the payment process if bank server is taking time or encounters any error, ensure that balance should not be deduct from user's account. | PD
1 | Rate trigger | To verify where a user sets a valid rate trigger by entering a specific gold rate. | PD
2 |  | To verify where a user sets a valid rate trigger by entering a specific silver rate. | PD
3 |  | Verify that the app accepts the input and saves the trigger configuration successfully. | PD
4 |  | To verify user sets a trigger by entering "Amount is Below". | PD
5 |  | To verify user sets a trigger by entering "Amount is Above". | PD
6 |  | Verify that the app detects and rejects the invalid input, displaying an appropriate error message. | PD
7 |  | To check the ability of the app to handle multiple rate triggers set by a user. | PD
8 |  | To check where the current gold/silver rate crosses the user-configured triggered rate and Verify that the app accurately detects the trigger activation and sends the notification. | PD
9 |  | Verify that users can set multiple triggers with different values for both gold and silver rates, and ensure that the app correctly saves. | PD
10 |  |  | PD
11 |  | To verify when triggered rate is matches with live rate, notification will be send through the chosen channel (SMS, WhatsApp, or email). | PD
12 |  | To verify where the gold rate increases or decreases significantly to validate that the notifications contain the correct information, including the current gold rate and relevant details. | PD
13 |  | Verify that users can choose to receive notifications through SMS, WhatsApp, or email based on their preferences, and ensure that the app delivers notifications through the selected channels accordingly. | PD
14 |  | To verify rate trigger history is generated correctly. | PD
15 |  | To verify user is able to cancel the rate trigger setting. | PD
16 |  | Verify user should not able to set trigger rate as live rate. | PD
17 |  | To verify user can set same trigger rate twice. | PD

## notification templates
SR NO. | SCENARIO | TEMPLATE SUGGESTED | MEDIUM | TEMPLATE TO BE USED
1 | OTP while registering for first time as a customer | Hello, Your One Time Password is {{1}} for login. Do not share this OTP with anyone. Egold | Email, SMS | Your One Time Password for registration is {{1}}. Do not share this OTP with anyone. {{tenant name}}
2 | OTP for forgot password | Hello, Your One Time Password is {{1}} for login. Do not share this OTP with anyone. Egold | Email, SMS | Your One Time Password for resetting password is {{1}}. Do not share this OTP with anyone. {{tenant name}}
3 | sign in with OTP | Hello, Your One Time Password is {{1}} for login. Do not share this OTP with anyone. Egold | SMS | Your One Time Password for login is {{1}}. Do not share this OTP with anyone. {{tenant name}}
4 | Rate trigger | Hello, Current rate of {{Gold / Silver}} has changed and met your expected rate. Please check and proceed for trade. E-Gold. | APP, SMS / EMAIL / WA | {{Gold / Silver}} rate is {{above/below}} {{trigger rate}}. Current rate is {{rate}}. {{tenant name}}
5 | Successful buy transaction | Hello, Transaction number (transaction ID) for Rs. {{amount}} is done successfully for purchase. Your weight balance has been upgraded. Thank you for choosing us. E-Gold | APP, SMS / EMAIL / WA | Your {{Gold/Silver}} {{Buy/Sell}} order of {{order wt}} grms is successfully executed by ID:{{order id}}. Happy shopping. {{tenant name}}
6 | Successful sell transaction | Hello, Transaction number (transaction ID) for Rs. {{amount}} is done successfully for sell. Your weight balance has been updated. Thank you for choosing us. E-Gold | APP, SMS / EMAIL / WA | Your {{Gold/Silver}} {{Buy/Sell}} order of {{order wt}} grms is successfully executed by ID:{{order id}}. Happy shopping. {{tenant name}}
7 | Successful delivery transaction | Hello, Transaction number (transaction ID) for Rs. {{amount}} is done about delivery. Your weight balance has been updated and you will receive your delivery soon. Thank you for choosing us. E-Gold | APP, SMS / EMAIL / WA | Your {{Gold/Silver}} delivery of {{delivery wt}} grms is successfully executed by ID:{{order id}}. {{tenant name}}
8 | SIP Started | Hello, Your {{Gold/Silver}} SIP of {{amount}} has started successfully and transaction will be done on {{Date}} of each month. Thank you for choosing us. E-Gold | APP, SMS / EMAIL / WA | Hello, Your {{Gold/Silver}} SIP of {{amount}} has started successfully and transaction will be done on {{Date}} of each month. Thank you for choosing us. {{tenant name}}
9 | SIP Reminder | Hello, This is a reminder about your upcoming SIP installment which is due on {{SIP Date}}. Please ensure sufficient balance in bank a/c XXXXXXXXXXX0000. Thank you, E-Gold. | APP, SMS / EMAIL / WA | We’d like to remind you that upcoming payment for {{amount}} will be due by [date] for {{Gold/Silver}} SIP. Please ensure sufficient balance in bank a/c XXXXXXXXXXX0000. Thank you. {{tenant name}}
10 | Successful monthly SIP transaction | Hello, Transaction number (transaction ID) for Rs. {{amount}} is done successfully for SIP {{SIP Number}}. Your weight balance has been updated. Thank you for choosing us. E-Gold | APP, SMS / EMAIL / WA | Your {{Gold/Silver}} SIP payment for {{amount}} is successfully executed for current month by ID:{{receipt id}}. {{tenant name}}
11 | Unsuccessful Buy transaction | Hello, Transaction of Rs. {{amount}} for buy has failed. Your weight balance and a/c balance hasn't been affected. Please check and try again. E-Gold | APP | Your transaction for {{Gold/Silver}} {{Buy/Sell}} order of {{order wt}} grms has failed. Please check and try again. {{tenant name}}
12 | Unsuccessful sell transaction | Hello, Transaction of Rs. {{amount}} for sell has failed. Your weight balance and a/c balance hasn't been affected. Please check and try again. E-Gold | APP | Your transaction for {{Gold/Silver}} {{Buy/Sell}} order of {{order wt}} grms has failed. Please check and try again. {{tenant name}}
13 | Unsuccessful SIP monthly installment transaction | Hello, Transaction of Rs. {{amount}} for monthly installment has failed for SIP {{SIP Number}}. Your weight balance and a/c balance hasn't been affected. Please check and try again. E-Gold | APP | Your transaction for {{Gold/Silver}} SIP of the current month has failed. Please check. {{tenant name}}
14 | Unsuccessful Delivery transaction | Hello, Transaction of Rs. {{amount}} for delivery has failed. Your weight balance and a/c balance hasn't been affected. Please check and try again. E-Gold | APP | Your transaction for {{Gold/Silver}} delivery of {{delivery wt}} grms has failed. Please check and try again. {{tenant name}}
15 | Delivery marked by tenant | Hello, With respect to your {{delivery transaction ID}}, your delivery of {{grams}} grams {{Silver/Gold}} is marked as delivered. Thank you for choosing us. E-Gold |  | Your {{Gold/Silver}} delivery of {{delivery wt}} grms for ID:{{order id}} is successfully marked as {{status: devlivered / in transit / out for delivery}}. Happy shopping. {{tenant name}}
16 | Profile update | Hello, Your profile has been updated successfully. E-Gold | APP | Your profile has been updated successfully. {{tenant name}}
17 | Adding / Updating Bank details | Hello, Bank details have been added & updated successfully in your account. E-Gold | APP | Bank details have been added & updated successfully in your account. {{tenant name}}
18 | Adding / updating nominee details | Hello, Nominee details have been added & updated successfully in your account. E-Gold | APP | Nominee details have been added & updated successfully in your account. {{tenant name}}
19 | Delivery updates | Hello, Your delivery against transaction number (transaction ID) will be delivered by today. Please ensure your availibility at provided address. Please note that ID proof is mandatory to accept your delivery. Thank you for choosing us. E-Gold | APP, SMS / EMAIL / WA | Your {{Gold/Silver}} delivery of {{delivery wt}} grms for ID:{{order id}} is successfully marked as {{status: devlivered / in transit / out for delivery}}. Happy shopping. {{tenant name}}