## TPM_Sheet
| Ticket ID : | TT2437 | Release Version :
| Project Name : | CU | Script Project Path :
| Module Name : |  | Test Cases Reviewed when :
| Release Version : |  | Testing Deadline :
| Ticket Owner : | Harshali Rananaware | Project Go live Date :
| Testing Owner : | AMreen Shaikh
Description | Connect us madhil Unpass che Point Pass karat astana Download karun Excel Sheet la Export kelyanantar "Is Confirmation Required (Yes/No)" He option tya formar madhye disat nahi tari te Add karun dene.
Testing server url, user name and password
Pre-condition
Dependencies:
Test Case# | Test description | Testing Type | Test Case Group | Module | Sub Module | Screenshot path | Excepted Result | Actual Result | Status | Priority | Severity | Developer remark | Tester remark | Tester remark | BA Remark | Test Case Created When | Testcase Created By | Version
TC_01 | To login with valid credentials and observe | Functional | Integration |  |  |  | Login should be done successfully | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_02 | To click on bulk upload format and observe | [5 empty] | CSV file should be saved | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_03 | To open csv file and observe | [5 empty] | File should be opened | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_04 | To check Type column functionality | Functional | Integration | Dashboard | Entry |  | It should be drop down and shoul display same data as CU |  | Fail |  |  |  |  | Pending |  | 30/05/2022 | Amreen
TC_05 | To check priority column functionality | Functional | Integration | Dashboard | Entry |  | It should be drop down and shoul display same data as CU |  | Fail |  |  |  |  | Pending |  | 30/05/2022 | Amreen
TC_06 | To check external ref no column functionality | Functional | Integration | Dashboard | Entry |  | Should accept characters,numeric value and symbols. |  | Fail |  |  |  |  | Pending |  | 30/05/2022 | Amreen
TC_07 | To check where ever required drop down is added or not | Functional | Integration | Dashboard | Entry |  | Type , priority, assign to dept, assign to person, is confirmation , type of issue, branch name for these column drop down should be added |  | Fail |  |  |  |  | Pending |  | 30/05/2022 | Amreen
TC_08 | To save and observe | Functional | Integration | Dashboard | Entry |  | CSV file should be saved | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_09 | To click on bulk upload and observe | Functional | Integration | Dashboard | Entry |  | Frame should display | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_10 | To click on choose file and observe | Functional | Integration | Dashboard | Entry |  | File manager page should display | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_11 | To select the file and click on upload | Functional | Integration | Dashboard | Entry |  | File should be upload successfully | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_12 | To check successfully msg is being displayed or not | Functional | Integration | Dashboard | Entry |  | SUccessfull msg should display | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_13 | To check record entered are being displayed properly or not | [5 empty] | Same entered data should display | Entered is confirmation as yes in csv upload file, no tick is being displayed in cu. | Fail | High | Critical | solved |  | Closed |  | 31/05/2022 | Amreen
TC_14 | To clcik on edit and observe | [5 empty] | Same entered data should display | Entered is confirmation as yes in csv upload file, no tick is being displayed in cu. | Fail | High | Critical | solved |  | Closed |  | 31/05/2022 | Amreen
TC_15 | To click on dashboard -> unpassed and observe | Functional | Integration | Dashboard | Unpassed |  | unpassed page should display | As expected | Pass | [6 empty] | 30/05/2022 | Amreen
TC_16 | To check data entered in csv file same data is being displayed in unpassed or not | Functional | Integration | Dashboard | Unpassed |  | Same data should be displayed | No records displayed | Pass | [6 empty] | 30/05/2022 | Amreen
TC_17 | To check is confirmation column added or not in grid view | Functional | Integration | Dashboard | Unpassed |  | Is confirmation shoulxd be added | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_18 | To check correct dta is being displayed in is confirmation or not | Functional | Integration | Dashboard | Unpassed |  | It should display valid data. | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_19 | To clcik on edit and observe | Functional | Integration | Dashboard | Unpassed |  | Same entered data should display | Entered is confirmation as yes in csv upload file, no tick is being displayed in cu. | Fail | High | Critical | solved |  | Closed |  | 31/05/2022 | Amreen
TC_20 | To click on export and observe | Functional | Integration | Dashboard | Unpassed |  | Csv file should be exported | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_21 | To check Passing Status column added or not | Functional | Integration | Dashboard | Unpassed |  | Passing Status should be added | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_22 | To check Passing Status column functionality | Functional | Integration | Dashboard | Unpassed |  | Drop down should be added |  | Fail |  |  |  |  | Pending |  | 31/05/2022 | Amreen
TC_23 | To check Passing remark column added or not | Functional | Integration | Dashboard | Unpassed |  | Passing remarktus should be added | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_24 | To check Passing Status column is mandatory or not | Functional | Integration | Dashboard | Unpassed |  | it should be mandatory | not mandatory | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_25 | To check Passing remark column is mandatory or not | Functional | Integration | Dashboard | Unpassed |  | it should be mandatory | not mandatory | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_26 | To check is confirmation column added or not | Functional | Integration | Dashboard | Unpassed |  | is confirmation should be added | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_27 | To check is confirmation column functionality | Functional | Integration | Dashboard | Unpassed |  | Drop down should be added |  | Fail |  |  |  |  | Pending |  | 31/05/2022 | Amreen
TC_28 | To check is confirmation column is mandatory or not | Functional | Integration | Dashboard | Unpassed |  | it should be mandatory | not mandatory | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_29 | To check Passing name column added or not | Functional | Integration | Dashboard | Unpassed |  | Passing name should be added | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_30 | To check is passing name is mandatory or not | Functional | Integration | Dashboard | Unpassed |  | it should be mandatory | not mandatory | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_31 | To check what if passig status is given as Passed | Functional | Integration | Dashboard | Unpassed |  | then reord should be added | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_32 | To check what if passig status is given as Unpass | Functional | Integration | Dashboard | Unpassed |  | then reord should be not added | record passes | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_33 | To check what if passig status is given as blank | Functional | Integration | Dashboard | Unpassed |  | then reord should be not added | record passes | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_34 | To check what if passig status is given as blank | Functional | Integration | Dashboard | Unpassed |  | Should donload the file with error msg | not being download | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_35 | To check what if passig remark is given | Functional | Integration | Dashboard | Unpassed |  | Passing remark should be aaded to the record | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_36 | To check what if passig remark is given as blank | Functional | Integration | Dashboard | Unpassed |  | then reord should be not added | record passes | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_37 | To check what if passig remark is given as blank | Functional | Integration | Dashboard | Unpassed |  | Should donload the file with error msg | not being download | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_38 | To check what if passig name is given | Functional | Integration | Dashboard | Unpassed |  | Passing name should be aaded to the record | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_39 | To check what if passig name is given as blank | Functional | Integration | Dashboard | Unpassed |  | then reord should be not added | record passes | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_40 | To check what if passig remark is given as blank | Functional | Integration | Dashboard | Unpassed |  | Should donload the file with error msg | not being download | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_41 | To check what if is confirmation is given yes | Functional | Integration | Dashboard | Unpassed |  | Is confirmation should be aaded to the record | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_42 | To check what if is confirmation is given no | Functional | Integration | Dashboard | Unpassed |  | Is confirmation should be aaded to the record | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_43 | to click on edit and observe same data is being displayed or not | Functional | Integration | Dashboard | Unpassed |  | Same data should display | As expected | Pass | [6 empty] | 31/05/2022 | Amreen
TC_44 | To check what if is confirmation is given as blank | Functional | Integration | Dashboard | Unpassed |  | then reord should be not added | record passes | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_45 | To check what if is confirmation is given as blank | Functional | Integration | Dashboard | Unpassed |  | Should donload the file with error msg | not being download | Fail |  |  | solved |  | Closed |  | 31/05/2022 | Amreen
TC_46
TC_47
TC_48
TC_49
TC_50
TC_51
TC_52
TC_53
TC_54
TC_55
TC_56
TC_57
TC_58

## TPM_MISC
Testing Type | Test case Group | Status | Severity | Priority | Tester remark | Developer remark | BA Remark | testcase created by
UI/UX | Smoke | Pass | Critical | High | Closed | Resolved | Closed | Amreen
Functional | Sanity | Fail | Major | Medium | Pending | Not a bug | Re-open | Maruti
Non-Functional | Regression | Partially Failed | Minor | Low | Re-open | Deffered | Deffered | Priyanka
| Functionality | Pending | Low |  |  | In-Progress |  | Monika
| Intergration | Under Development | [5 empty] | Abhijeet
Validation